## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas | SM/18866 | Augmentation | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaparpuri & Adjoining Mouzas (Jalghata), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000336/2024-2025 | 2770/AD | 28/06/2024 | 26/09/2024 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 126.53 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas | SM/18866 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Kaparpuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] (SM/18866) | Assistant Engineer | Junior Engineer | ORD/000062/2025-2026 | 1438/SMD | 21/05/2025 | 03/10/2025 | M/S. S.S. ENTERPRISE | 18.64 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas | SM/18866 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/002390/2023-2024 | 1213/AD | 29/02/2024 | 11/04/2025 | J H L CONSTRUCTION | 6.9 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of ground water based piped water supply scheme for Kaparpuri & adjoining mouzas | SM/18866 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000346/2024-2025 | 2787/AD | 01/07/2024 | 27/02/2025 | AQUATECH ENGINEER | 34.45 | 0 | 0 | 100
Total | [13 empty] | 186.52 | 0 | 0