## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) | SM/18867 | Augmentation | Construction of Boundary Wall at proposed OHR site of Moukhali Water Supply Scheme (Block: Budge Budge-I) under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000516/2022-2023 | 5537/AD | 29/09/2022 | 13/11/2022 | M/S. S.S. ENTERPRISE | 16.2 | 0 | 0 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) | SM/18867 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 3044/AD | 28/09/2023 | 28/09/2023 | Resource Division | 77.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) | SM/18867 | Augmentation | Construction of Chlorination Room at proposed OHR Site of Moukhali W/S Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000520/2022-2023 | 5507/AD | 29/09/2022 | 13/11/2022 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 5.46 | 0 | 0 | 10
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MOUKHALI W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE (PHASE-II) | SM/18867 | Augmentation | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap within Moukhali W/S Scheme of Budge Budge - I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. (SM/18867) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000604/2024-2025 | 4098/AD | 03/10/2024 | 27/03/2026 | M.M. ENTERPRISE | 144.41 | 0 | 0 | 10
Total | [13 empty] | 243.59 | 0 | 0