## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) | SM/18872 | Augmentation | Laying distribution system of piped water supply at Zone- XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000874/2024-2025 | 4658/AD | 20/11/2024 | 19/01/2025 | M/S. JHARNA ENTERPRISE | 29.11 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) | SM/18872 | Augmentation | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, boundary wall and other allied works at Zone- XV of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10532 & SM/18872) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000432/2024-2025 | 3275/AD | 07/08/2024 | 03/06/2025 | PINKI CONSTRUCTION | 129.16 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS UNDER ZONE-XV, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS I/C/W JJM UNDER MEGA SURFACE WATER BASED W/S/S FOR FALTA-MATHURAPUR UNDER ALIPORE DIVISION, PHE DTE. (PHASE-II) | SM/18872 | Augmentation | Construction of approach road for Over Head Reservoir site at Zone ¿ XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000873/2024-2025 | 4657/AD | 20/11/2024 | 04/01/2025 | L.N. ENTERPRISE | 12.97 | 0 | 0 | 100
Total | [13 empty] | 171.25 | 0 | 0