## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Kashinagar Water Supply Scheme (Augmentation), Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001410/2023-2024 | 4596/AD | 14/12/2023 | 13/01/2024 | AQUATECH ENGINEERS | 18.31 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Kashinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001429/2023-2024 | 4619/AD | 14/12/2023 | 18/03/2025 | GARGO TRADERS | 557.6 | 0 | 0 | 50
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 07/11/2024 | GARGO TRADERS | 471.61 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Augmentation of Kashinagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I |  | ORD/001550/2023-2024 | 4764/SMD | 06/12/2023 | 06/03/2024 | T.S. CONSTRUCTION | 10.53 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Kashinagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18873) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000215/2024-2025 | 2598/AD | 19/06/2024 | 03/08/2024 | M/S AINUR ENTERPRISE | 9.73 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( KASINAGAR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001363/2023-2024 | 3259/AD | 05/10/2023 | 19/11/2023 | LEMNISCATE | 5.75 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter at 3rd Tubewell Site of Kashinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000322/2024-2025 | 2397/AD | 07/06/2024 | 07/07/2024 | S. CHAKRABORTY AND CO. | 19.95 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KASINAGAR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN KAKDWIP BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24PARGANAS DISTRICT | SM/18873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000999/2023-2024 | 1792/AD | 27/03/2024 | 27/03/2024 | Resource Division | 33.67 | 0 | 0 | 0
Total | [13 empty] | 1128.09 | 0 | 0