## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 02/09/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 329.42 | 49.29 | 40
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd Tubewell site for Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000386/2024-2025 | 3082/AD | 25/07/2024 | 08/09/2024 | ARUSHI CONSTRUCTION | 7.18 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 4th Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000388/2024-2025 | 3084/AD | 25/07/2024 | 24/08/2024 | M/S. DAS BUILDERS | 11.75 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Construction, Placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. at Naraharipur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000182/2024-2025 | 2541/AD | 18/06/2024 | 01/09/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 78.34 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000387/2024-2025 | 3083/AD | 25/07/2024 | 08/09/2024 | SWAPAN KUMAR PRADHAN | 34.22 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAHARIPUR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001359/2023-2024 | 3256/AD | 05/10/2023 | 19/11/2023 | VOYAGER | 6.35 | 6.35 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.2 | 24.99 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Naraharipur PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002610/2023-2024 | 377/KSD | 21/02/2024 | 26/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000969/2023-2024 | 1762/AD | 27/03/2024 | 27/03/2024 | Resource Division | 43.44 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAHARIPUR PWSS (PHASE-B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPOR DIVISION IN SOUTH 24 PARGANAS DISTRICT | SM/18876 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Naraharipur W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000159/2024-2025 | 2510/AD | 15/06/2024 | 22/12/2024 | SIMPLEX DRILLING CO. | 51.43 | 23.4 | 45.5 | 100
Total | [13 empty] | 902.32 | 359.86 | 39.88