## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGASAGAR (ZONE - I & II) PWSS (PHASE - B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001362/2023-2024 | 3436/AD | 12/10/2023 | 26/11/2023 | VOYAGER | 7.61 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002622/2023-2024 | 865(A)/KSD | 13/12/2023 | 23/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000716/2023-2024 | 486/AD | 24/01/2024 | 24/01/2024 | Resource Division | 13.4 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000968/2023-2024 | 1760/AD | 27/03/2024 | 27/03/2024 | Resource Division | 29.12 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000903/2023-2024 | 889/AD | 07/02/2024 | 07/02/2024 | Resource Division | 67.34 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Payment for New Service connection PHED, Ganga Sagar Mouza Zone-I PH-III W/ Scheme Near Helipad Application No:- 1007971659 Reference ID: 106689505 |  |  | BILL/01156/2024-2025 | BP-2024-25-232 | 08/08/2024 | 08/08/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Ganga Sagar Mouza Zone-I PH-4 (PHE Campus 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000718/2024-2025 | 3424/SMD | 28/10/2024 | 26/04/2025 | T.S. CONSTRUCTION | 8.61 | 0 | 0 | 95
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Ganga Sagar Mouza Zone-I PH-3 (Near Helipad) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000719/2024-2025 | 3425/SMD | 28/10/2024 | 26/01/2025 | M/S. BABUSONA ENTERPRISE | 8.22 | 0 | 0 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Supply and installation on hire basis Printed Flex Banner for Creating Public Awareness on JJM for different area of Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001334/2024-2025 | 5423/AD | 24/12/2024 | 23/01/2025 | SHOUMMODIP AND CO. | 11.44 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main and FHTC for 1 year after completion of FHTC works for Augmentation of Gangasagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002231/2023-2024 | 904/AD | 08/02/2024 | 01/04/2026 | ANUP PAUL | 390.45 | 0 | 0 | 30
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGASAGAR (ZONE - I & II) PWSS (PHASE - B) TO ACCOMMODATE FHTC IN SAGAR BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/18983 | Augmentation | Laying distribution system for providing FHTC for Augmentation of Gangasagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-B) (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000423/2024-2025 | 4440/AD | 06/11/2024 | 07/05/2025 | PIKASU BOSE | 126.64 | 0 | 0 | 100
Total | [13 empty] | 667.51 | 0 | 0