## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001619/2021-2022 | 622/KSD | 05/10/2021 | 12/10/2021 | ROY CHOWDHURY ASSOCIATES | 3.31 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001610/2021-2022 | 608/KSD | 27/09/2021 | 04/10/2021 | ROY CHOWDHURY ASSOCIATES | 4.57 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001030/2021-2022 | 544/KSD | 01/09/2021 | 21/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.57 | 4.57 | 99.85 | 98
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000492/2023-2024 | 4791/AD | 19/12/2023 | 19/12/2023 | Resource Division | 28.85 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone I W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000403/2024-2025 | 3186/AD | 31/07/2024 | 29/09/2024 | C L B SYNDICATE | 58.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Augmentation of Narayanpur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I |  | ORD/001481/2023-2024 | 4762/SMD | 06/12/2023 | 06/03/2024 | R.N.S. TRADING | 19.32 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Narayanpur W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000218/2024-2025 | 2601/AD | 19/06/2024 | 19/07/2024 | CHANDRA ENTERPRISE | 9.59 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone II W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000330/2024-2025 | 2733/AD | 25/06/2024 | 24/08/2024 | M/S B. ENTERPRISE | 117.78 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAYANPUR )) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001364/2023-2024 | 3437/AD | 12/10/2023 | 26/11/2023 | M/S R.DUTTA & CO. | 15.05 | 15.05 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.31 | 33.16 | 90
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Narayanpur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002617/2023-2024 | 894/KSD | 18/12/2023 | 23/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000792/2023-2024 | 637/AD | 30/01/2024 | 30/01/2024 | Resource Division | 24.89 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000547/2023-2024 | 30/AD | 02/01/2024 | 02/01/2024 | Resource Division | 22.85 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 5157/AD | 12/12/2024 | 12/12/2024 | Resource Division | 123.2 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 Nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 2647] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001142/2023-2024 | 3655/AD | 31/10/2023 | 01/04/2026 | M/S B. ENTERPRISE | 470.08 | 343.74 | 73.12 | 92
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001453/2023-2024 | 1190/AD | 28/02/2024 | 27/04/2025 | SAFTI PRIVATE LIMITED | 31.47 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001419/2023-2024 | 1575/AD | 16/03/2024 | 30/03/2025 | SAFTI PRIVATE LIMITED | 18.21 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001420/2023-2024 | 1576/AD | 16/03/2024 | 30/03/2025 | SAFTI PRIVATE LIMITED | 13.36 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Laying distribution system along with Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main & FHTC for 01 year after completion of FHTC work for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001452/2023-2024 | 4690/AD | 18/12/2023 | 17/03/2024 | M/S SWAPAN KUMAR PRADHAN | 79.34 | 51.5 | 64.91 | 50
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Repairing of Pump House and Boundary wall with construction of approach road at 3rd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002216/2024-2025 | 2111/KSD | 30/12/2024 | 14/01/2025 | AZAD RAHAMAN LASKAR | 2.32 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Negotiation of price for Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 & 4 of Augmentation of Narayanpur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/002552/2023-2024 | 4758/SMD | 06/12/2023 | 06/12/2025 | DIPA CHHETRI | 19.08 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Repairing of Pump House and Boundary wall with construction of approach road at 2nd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002215/2024-2025 | 2110/KSD | 30/12/2024 | 14/01/2025 | AZAD RAHAMAN LASKAR | 2.58 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 50000 Gallon at Narayanpur W/S Scheme, Block - Namkhana, South 24 Parganas under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000150/2025-2026 | 2672/AD | 09/06/2025 | 14/07/2026 | SUPREME NIRMAN UDYOG | 131.79 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18128) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/002525/2024-2025 | 810/AD | 27/02/2025 | 29/03/2025 | SIMPLEX DRILLING CO. | 20.37 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanganj W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15046) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002589/2024-2025 | 921/AD | 05/03/2025 | 04/04/2025 | M/S P. B. CONSTRUCTION | 7.18 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Continuation order for Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003232/2023-2024 | 370/KSD | 19/02/2024 | 19/11/2024 | BIMALENDU GIRI | 0.61 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000149/2025-2026 | 2671/AD | 09/06/2025 | 24/07/2025 | FREEDOM CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.06 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell site of Narayanpur W/S Scheme (Augmentation), Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000118/2024-2025 | 2395/AD | 07/06/2024 | 01/12/2024 | SARADA CONSTRUCTION | 39.9 | 0 | 0 | 50
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Construction of brick platform, Road Restoration, for Augmentation of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- I and II) (Part-B) (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000458/2024-2025 | 3417/AD | 21/08/2024 | 20/10/2024 | ANANTA KUMAR GIRI | 68.28 | 0 | 0 | 100
30 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | New Service connection and security deposit for Narayanpur PH-4 under JJM Application No-1008616915 Ref ID- 107086019 |  |  | BILL/01058/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.36 | 0 | 0 | 0
31 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/18984 | Augmentation | Payment for new Service connectioon Narayanpur W/S Scheme PH- 3 Application No- 1008284289 Reference ID:- 106871858 |  |  | BILL/00256/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.97 | 0 | 0 | 0
Total | [13 empty] | 1354.73 | 415.65 | 30.68