## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Arrangement of Executive triple bed at Lindsay Hotel for 3 (three) nos. guest in connection with Jal Jeevan Mission under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/001246/2024-2025 | 5144/AD | 12/12/2024 | 13/12/2024 | TANMAY ROY CHOWDHURY | 0.1 | 0 | 0 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Arrangement of Executive Double bed at Lindsay Hotel for 2 (two) nos. guest in connection with Jal Jeevan Mission under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/001245/2024-2025 | 5143/AD | 12/12/2024 | 13/12/2024 | TANMAY ROY CHOWDHURY | 0.08 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Supplying of office meeting related stationary materials in connection with Block Orientation Programme for JJM works under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/002680/2023-2024 | 2952/AD | 22/09/2023 | 29/09/2023 | UNIQUE AGENCY (PARTNER) | 7.34 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Orientation and Mass Awareness Generation (IEC) Activities related to judicious and safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) support Activities at South 24 Parganas District under Alipore Division, P.H.E. Dte. (for 29 Blocks)Blocks : Budge -I, Budge -II, Bishnupur -I, Bishnupur -II, Bhangar -I, Bhangar -II, Baruipur, Thakurpukur Maheshtala, Joynagar -I, Joynagar -II, Kultali, Magarhat -I, Mandirbazar, Sonarpur , Kakdwip, Patharpratima, Sagar, Namkhana, Falta, Diamond -I, Diamond-II, Kulpi, Mathurapur -I, Mathurapur -II, Magrahat-II, Canning -I, Canning -II, Gosaba and Basanti. | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/002361/2023-2024 | 1180/AD | 28/02/2024 | 01/09/2025 | DEBNATH BROTHERS NEW ACC | 140.23 | 0 | 0 | 75
5 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Falta and Diamond -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000511/2024-2025 | 2720/AD | 24/06/2024 | 24/07/2024 | BHUMI FOUNDATION | 3.24 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Mathurapur -I and Mathurapur -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000519/2024-2025 | 2722/AD | 24/06/2024 | 24/07/2024 | BHUMI FOUNDATION | 3.24 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Kulpi and Diamond Harbour -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000514/2024-2025 | 2721/AD | 24/06/2024 | 24/07/2024 | BHUMI FOUNDATION | 3.4 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Diamond Harbour-II Location : - Zone-II (Augmentation-SM/15531), Kalikamerya of Sarish GP (Main Scheme - SM/12577), Zone-VI (Retrofitting-SM/09506), Zone Left out areas of Zone-VI (Augmentation-SM/14890). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003120/2023-2024 | 710/AD | 31/01/2024 | 15/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Diamond Harbour-II Location : - Zone-VI (Augmentation-SM/13916), Zone-V (Retrofitting-SM/09505), Zone-Left out areas of Zone-V (Augmentation-SM/14463), Zone-V (Augmentation-SM/13915). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003121/2023-2024 | 711/AD | 31/01/2024 | 15/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Falta Location : - Zone - VIII (Augmentation-SM/14473), Zone - VIII (Augmentation-SM/14468), Zone - V (Retrofitting-SM/08122), Zone - V (Augmentation-SM/14477). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003126/2023-2024 | 794/AD | 03/02/2024 | 18/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Falta Location : - Zone - III (Retrofitting-SM/08120), Zone - III (Augmentation-SM/13969), Zone - IIIB Dostipur (Augmentation-SM/14465), Zone - VIII (Retrofitting-SM/09425). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003125/2023-2024 | 739/AD | 02/02/2024 | 17/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Kulpi Location : - Ramnagar Gazipur (Main Scheme - SM/12755), Bijoyrampur of Kamarchak GP (Main Scheme -SM/12756), Zone - XIII (Augmentation - SM/13910), Chak Ruplaskar of Ramkishore GP (Main Scheme - 13961). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003134/2023-2024 | 939/AD | 08/02/2024 | 23/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Kulpi Location : - Zone-III (Augmentation -SM/15529), Zone-IV (Augmentation - SM/18549). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003135/2023-2024 | 940/AD | 08/02/2024 | 23/02/2024 | UNIQUE AGENCY (PARTNER) | 0.48 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Kulpi Location : - Zone-VIII(B) (Augmentation - SM/15320), Zone- X (Augmentation-SM/18553), Bhairabitala of Keoratala GP (Main Scheme-SM/12759), Anduldaha Gopalpur of Karanjali GP (Main Scheme-SM/13964). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003132/2023-2024 | 937/AD | 08/02/2024 | 23/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Kulpi Location : - Kabasenre (Main Scheme - SM/12757), Dakshin Ramkrishnapur Zone-I (Retrofitting - SM/09973), Zone-I - (Augmentation - SM/18550), Kamarchak (Main Scheme - SM/13073). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003130/2023-2024 | 849/AD | 05/02/2024 | 20/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at South 24 Parganas District | SM/19092 | Support-IEC | Erection of display board on Swajal Gram/Har Ghar Jal Village at various location within South 24 - Parganas District under Alipore Division, PHE. Dte. Block Name - Kulpi Location : - Karanjali (Main Scheme - SM/13963), Zone - XI (Augmentation-SM/13909), Zone-VII (Augmentation - SM/18400), Zone-VIII(A) (Augmentation - SM/18552). | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003131/2023-2024 | 900/AD | 07/02/2024 | 22/02/2024 | UNIQUE AGENCY (PARTNER) | 0.96 | 0 | 0 | 100
Total | [13 empty] | 165.81 | 0 | 0