## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Laboratory Maintenance charges of District Water Testing Laboratory at Bijoygarh under Alipore Division, PHE Dte.(upcoming one year). | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/001182/2023-2024 | 580/RWS | 10/11/2023 | 09/11/2024 | M/S JBL CONSTRUCTION | 0.94 | 0.94 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Basanti Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May'2025. N.I.B-06/RWS of 2024-25, Sl no-10 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003575/2024-2025 | 1148D/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Canning Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April'2025& May'2025. N.I.B-06/RWS of 2024-25, Sl no-11 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003577/2024-2025 | 1148E/RWS | 26/03/2025 | 26/05/2025 | M/S. S.S. ENTERPRISE | 0.73 | 0.68 | 92.86 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April'2025. N.I.B-06/RWS of 2024-25, Sl.no-3 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003560/2024-2025 | 1147C/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant,Sampling Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Ramganga Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March' 2025. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003554/2024-2025 | 1040/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.5 | 95 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Kakdwip Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May' 2025 N.I.B-06/RWS of 2024-25, Sl no-6 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003571/2024-2025 | 1147F/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March'2025. N.I.B-05/RWS of 2024-25, Sl no-2 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003546/2024-2025 | 1038B/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Bakkhali Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May'2025. N.I.B-06/RWS of 2024-25, Sl no-8 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003573/2024-2025 | 1148B/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.64 | 0.64 | 100 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant & Lab.Attendent for 02 nos P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory & Raidighi Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May'2025 N.I.B-06/RWS of 2024-25, Sl no-17 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003583/2024-2025 | 1149E/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.83 | 0.83 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Agency charges for actual travelling expenses and IEC activites to the Laboratory personnel of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex under Alipore Division, PHE Dte.for the month of March'2025, April'2025 & May'2025. N.I.B-06/RWS of 2024-25, Sl no-18 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003584/2024-2025 | 1149F/RWS | 26/03/2025 | 26/06/2025 | M/S. S.S. ENTERPRISE | 0.6 | 0 | 0 | 90
11 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Ramganga Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May' 2025 N.I.B-06/RWS of 2024-25, Sl no-13 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003579/2024-2025 | 1149A/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.5 | 95 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Basanti Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March'2025. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003552/2024-2025 | 1039B/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant, Sampling Assistant & Lab.Attendent for 02 nos P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory & Raidighi Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March'2025 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003556/2024-2025 | 1044/RWS | 28/02/2025 | 31/03/2025 | M/S. S.S. ENTERPRISE | 0.83 | 0.83 | 100 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Kakdwip Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April' 2025 N.I.B-06/RWS of 2024-25, Sl no-5 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003570/2024-2025 | 1147E/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist,Bacteriologist,Lab.Assistant,Sampling Assistant of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex under Alipore Division, PHE Dte.for the month of March'2025. N.I.B-05/RWS of 2024-25, Sl no-1 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003545/2024-2025 | 1038A/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.97 | 0.94 | 97.3 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist,Bacteriologist ,Lab.Assistant,Sampling Assistant of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex under Alipore Division, PHE Dte.for the month of April'2025 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003557/2024-2025 | 1147A/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.97 | 0.94 | 97.3 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist,Bacteriologist,Lab.Assistant,Sampling Assistant of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex under Alipore Division, PHE Dte.for the month of May'2025. N.I.B-06/RWS of 2024-25, Sl no-2 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003559/2024-2025 | 1147B/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.97 | 0.94 | 97.3 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May'2025. N.I.B-06/RWS of 2024-25, Sl no-4 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003561/2024-2025 | 1147D/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant & Lab.Attendent for 02 nos P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory & Raidighi Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April'2025 N.I.B-06/RWS of 2024-25, Sl no-16 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003582/2024-2025 | 1149D/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.83 | 0.83 | 100 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Bhangor Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April' 2025 N.I.B-06/RWS of 2024-25, Sl no-14 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003580/2024-2025 | 1149B/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Bhangor Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of May' 2025 N.I.B-06/RWS of 2024-25, Sl no-15 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003581/2024-2025 | 1149C/RWS | 26/03/2025 | 01/06/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Ramganga Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April' 2025 N.I.B-06/RWS of 2024-25, Sl no-12 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003578/2024-2025 | 1148F/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.5 | 95 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant,Sampling Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Bakkhali Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March'2025. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003551/2024-2025 | 1039A/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.64 | 0.64 | 100 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Canning Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March'2025. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003553/2024-2025 | 1039C/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.37 | 0.37 | 100 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist, Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Bhangor Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March' 2025 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003555/2024-2025 | 1043/RWS | 28/02/2025 | 31/03/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
26 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant for 01 nos P.H.E Dte. Water Testing Laboratories (Kakdwip Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of March' 2025. N.I.B-05/RWS of 2024-25, Sl no-3 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003550/2024-2025 | 1038C/RWS | 27/02/2025 | 30/03/2025 | M/S. S.S. ENTERPRISE | 0.59 | 0.59 | 100 | 100
27 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant,Sampling Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Bakkhali Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April'2025. N.I.B-06/RWS of 2024-25, Sl no-7 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003572/2024-2025 | 1148A/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.64 | 0.64 | 100 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/Bacteriologist,Laboratory Assistant & Lab.Attendent for 01 nos P.H.E Dte. Water Testing Laboratories (Basanti Sub-District Laboratory) under Alipore Division, PHE Dte.for the Month of April'2025. N.I.B-06/RWS of 2024-25, Sl no-9 | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/003574/2024-2025 | 1148C/RWS | 26/03/2025 | 25/04/2025 | M/S. S.S. ENTERPRISE | 0.52 | 0.52 | 100 | 100
29 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Maintenance bill of Kensily Azad sporting Club SDWTL from April-24 to Sept-2024 |  |  | BILL/02190/2024-2025 | BP-2024-25-988 | 17/02/2025 | 17/02/2025 | KENSILY AZAD SPORTING CLUB | 0.22 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Half-yearly Maintenance Bill(June-24 to Nov-24) |  |  | BILL/02191/2024-2025 | BP-2024-25-987 | 17/02/2025 | 17/02/2025 | PASCHIMBANGA VIGYAN MANCHA | 0.44 | 0 | 0 | 0
31 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/ Bacteriologist and Laboratory Assistant for 04 nos. P.H.E Dte. Water Testing Laboratories (Kakdwip Sub-District Laboratory, Ramganga Sub-District Laboratory, Raidighi Sub-District Laboratory, Basanti Sub-District Laboratory) under Alipore Division, PHE Dte. (For one year from the date of issuance of Work Order) (2nd Call) | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000101/2025-2026 | 2530/AD | 30/05/2025 | 30/05/2026 | M/S. S.S. ENTERPRISE | 29.26 | 7.08 | 24.19 | 35
32 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab Assistant of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex under Alipore Division, PHE Dte. (For one year from the date of issuance of Work Order) (2nd Call) | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000099/2025-2026 | 2528/AD | 30/05/2025 | 30/05/2026 | M/S. S.S. ENTERPRISE | 8.57 | 2.08 | 24.31 | 35
33 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of Chemist/ Bacteriologist and Laboratory Assistant for 05 nos. P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory, Bhangor Sub-District Laboratory, Canning Sub-District Laboratory, Bakkhali Sub-District Laboratory, Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte. (For one year from the date of issuance of Work Order) (2nd Call) | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000100/2025-2026 | 2529/AD | 30/05/2025 | 30/05/2026 | M/S. S.S. ENTERPRISE | 36.58 | 8.85 | 24.19 | 35
34 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of 10 (Ten) nos. Lab. Personnel (Sampling Assistant and Lab. Attendant), actual travelling expenses and IEC activities to the Laboratory personnel for 07 nos. Laboratories (South 24 Parganas District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory) in the District. of South 24 Parganas under Alipore Division, PHE Dte. (For one year from the date of issuance of Work Order) (2nd Call) | Assistant Engineer, RWS,Assistant Engineer,HQ-II | Junior Engineer,RWS | ORD/000102/2025-2026 | 2531/AD | 30/05/2025 | 30/05/2026 | M/S. S.S. ENTERPRISE | 20 | 3.99 | 19.96 | 35
35 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Honorarium of Chemist,Bacteriologist,Lab.Assistant of general water testing laboratory from Dec-2025 to Feb-2026.(03 months) |  |  | BILL/00193/2026-2027 |  | 22/04/2026 | 22/04/2026 | KENSILY AZAD SPORTING CLUB | 1.35 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Honorarium of Chemist,Bacteriologist,Lab.Assistant of Sagar Mangal SDWTL from Dec-2025 to Feb-2026.(03 months) |  |  | BILL/00192/2026-2027 |  | 22/04/2026 | 22/04/2026 | SAGAR MANGAL SUB- DISTRICT WTL | 1.35 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Maintenance billfor expenditure of Sagar Mangalunder Alipore Division, PHE Dte. (March'23 to August'23) |  |  | BILL/01903/2023-2024 |  | 16/10/2023 | 16/10/2023 | SAGAR MANGAL | 0.4 | 0 | 0 | 0
38 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Festival bonus of Lab personnel under Alipore Division, PHE Dte. |  |  | BILL/01902/2023-2024 |  | 16/10/2023 | 16/10/2023 | SAGAR MANGAL | 0.16 | 0 | 0 | 0
39 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Maintenance bill for expenditure of Sagar Mangal Sub District Water Testing Laboratories under Alipore Division. |  |  | BILL/02077/2023-2024 |  | 15/03/2024 | 15/03/2024 | SAGAR MANGAL | 0.4 | 0 | 0 | 0
40 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remunearation of the lab personnel From January-2026 to March-2026 for the Lab at RKMLSP Campus,Narendrapur |  |  | BILL/00224/2026-2027 |  | 24/04/2026 | 24/04/2026 | RAMKRISHNA MISSION ASHRAMA | 1.35 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Honorarium of Chemist,Bacteriologist ,Lab Assistant of Sagar Mangal SDWTL from Sept-2025 to Nov-2025 |  |  | BILL/01686/2025-2026 |  | 11/02/2026 | 11/02/2026 | SAGAR MANGAL SUB- DISTRICT WTL | 1.35 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Bill for maintenance of Kensily Azad Sporting Club from Oct-2023 to Mar-2024 (06 month) |  |  | BILL/03334/2024-2025 |  | 19/09/2024 | 19/09/2024 | KENSILY AZAD SPORTING CLUB | 0.29 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Honorarium of Chemist,Bacteriologist & Lab Assistant of Kensily Azad Sporting Club SDWTL from Sept-2025 to Nov-2025. |  |  | BILL/01685/2025-2026 |  | 11/02/2026 | 11/02/2026 | KENSILY AZAD SPORTING CLUB | 1.35 | 0 | 0 | 0
44 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of the Lab personnel for the period from Oct-2025 to Dec-2025 for RKMLSP Campus,Narendrapur |  |  | BILL/00196/2026-2027 |  | 22/04/2026 | 22/04/2026 | RAMKRISHNA MISSION ASHRAMA | 1.35 | 0 | 0 | 0
45 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Remuneration of the Lab personnel for the period from Oct-2025 to Dec-2025 for Raidighi Nibodhata Lab,Mathurapur Campus. |  |  | BILL/00195/2026-2027 |  | 22/04/2026 | 22/04/2026 | RAMKRISHNA MISSION ASHRAMA | 1.35 | 0 | 0 | 0
46 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 15 NOS. PHED AND NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y - 2023-2024. | SM/19286 | Support-WQMSP | Honorarium for lab.personnel for Paschim Banga Vigyan Mancha SDWTL for the period from Sep-2025 to January-2026(05 months) |  |  | BILL/00194/2026-2027 |  | 22/04/2026 | 22/04/2026 | PASCHIMBANGA VIGYAN MANCHA | 2.25 | 0 | 0 | 0
Total | [13 empty] | 126.23 | 39.39 | 31.21