## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for Nandakumarpur, Zone-II, PH-1 w/s scheme till the restoration of WBSEDCL power supply under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003203/2020-2021 | 81/SMSD/I/AMP | 02/06/2020 | 22/06/2020 | M/S. PS & ASSOCIATES | 0.9 | 0.9 | 100 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Emergency hiring charges of 40 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-3 of Dharmatala water supply scheme Canning-I Block under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003211/2020-2021 | 72/AMP/SMSD | 07/06/2020 | 27/06/2020 | SRI KRISHNA NIRMAN | 0.97 | 0.97 | 100 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Emergency hiring charges of 30 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-3 of Dakshin Redokhali water supply scheme Canning-I Block under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003212/2020-2021 | 50/AMP/SMSD | 03/06/2020 | 23/06/2020 | SRI KRISHNA NIRMAN | 0.79 | 0.79 | 100 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for Kumirmari W/S Scheme under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003205/2020-2021 | 177/SMSD. | 01/04/2020 | 11/04/2020 | S.P. CONSTRUCTION | 0.97 | 0.95 | 97.79 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003238/2020-2021 | 516 of EE/SMD of 21-22 | 26/02/2021 | 18/03/2021 | J.D.J ENTERPRISE | 4.98 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Pet preform for Rana Paschim Pmnagar Bottling Plant Bottling Plant Unit in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000891/2021-2022 | 531/SMD | 06/04/2021 | 26/04/2021 | ALOK ENTERPRISE | 4.95 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for Supply & delivery of Pet preform for Rana Paschim Pmnagar Bottling Plant Bottling Plant Unit in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000892/2021-2022 | 609/SMD | 17/05/2021 | 06/06/2021 | ALOK ENTERPRISE | 4.95 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to different locations to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000846/2021-2022 | 307/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.55 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for Supply & delivery of Pet preform for Rana Paschim Pmnagar Bottling Plant Bottling Plant Unit in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical | Assistant Engineer -I | Junior Engineer | ORD/000890/2021-2022 | 552/SMD | 19/04/2021 | 09/05/2021 | ALOK ENTERPRISE | 4.95 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Emergency Carrying charges of 40 KVA Mobile silent type DG set on the situation of "AMPHAN" 2020 for Nandakumarpur Zone-I PH-1 water supply scheme under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003418/2020-2021 | 16/SMSD/I/AMP | 19/05/2020 | 18/06/2020 | SRI KRISHNA NIRMAN | 0.09 | 0.09 | 100 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and Installation of 25KVA voltage stabilizer at PH NO-1 of Nagendrapur water supply scheme under S.24 pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003240/2020-2021 | 2272/SMD | 27/07/2020 | 16/08/2020 | M.S.C ENTERPRISE | 4.63 | 4.63 | 100 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & different areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000694/2021-2022 | 32/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at PH-2, Zone-II of Nandakumarpur water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000749/2021-2022 | 88/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 0.99 | 0.99 | 100 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000732/2021-2022 | 4/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at Harindanga PH-1 w/s scheme of Falta Block under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000733/2021-2022 | 1518/A/AE-II/SMD.. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.9 | 0.9 | 100 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000695/2021-2022 | 22/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000697/2021-2022 | 29/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to different locations for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000725/2021-2022 | 12/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000736/2021-2022 | 3/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing DG set at PH-1 of Hesamabad w/s scheme under Kakdwip Sub-Division for preparedness of super cyclonic strom YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000698/2021-2022 | 182/YAAS/SMD. | 08/06/2021 | 28/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.36 | 2.36 | 100 | 0
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules at Dharmatala W/S Scheme under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003204/2020-2021 | 1147/SMSD | 31/12/2020 | 15/01/2021 | M/S. PS & ASSOCIATES | 8.61 | 0.86 | 10 | 0
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for supply and delivery of Gunny bag at Sagar Island in connection with preparedness of cyclonic strom YAAS under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000737/2021-2022 | 155/YAAS/SMD. | 29/05/2021 | 18/06/2021 | S.P. CONSTRUCTION | 4.94 | 4.94 | 100 | 0
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000702/2021-2022 | 19/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.3 | 0.3 | 100 | 0
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000703/2021-2022 | 10/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
25 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000705/2021-2022 | 11/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
26 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000707/2021-2022 | 33/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
27 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000709/2021-2022 | 27/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
28 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000710/2021-2022 | 25/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
29 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000711/2021-2022 | 26/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
30 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000712/2021-2022 | 28/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
31 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000714/2021-2022 | 24/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
32 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to various places for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000715/2021-2022 | 5/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
33 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & several locations for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000717/2021-2022 | 18/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.9 | 0.9 | 100 | 0
34 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at O.H.R No-43 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000675/2021-2022 | 74/YASS/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 1.94 | 1.94 | 100 | 0
35 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & several locations for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000719/2021-2022 | 30/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
36 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply and delivery of Polyfilm roll fot pouch form form fill seal machine at D.Roypur Bottling Plant Unit NO-1 in connection with preparedness of cyclonic storm "YAAS" South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000720/2021-2022 | 163-YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 4.97 | 4.97 | 100 | 0
37 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at Chandokhali (BS-II) water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000680/2021-2022 | 63-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 0.92 | 0.92 | 100 | 0
38 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at Sikharbali GP water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000681/2021-2022 | 79-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.08 | 1.08 | 100 | 0
39 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply and delivery of Gunny bag D.Roypur Bottling Plant Unit No-1 in connection with prepardness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000684/2021-2022 | 152-YAAS/SMD | 29/05/2021 | 18/06/2021 | S.P. CONSTRUCTION | 4.94 | 4.94 | 100 | 0
40 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply and delivery of Gunny bag D.Roypur Bottling Plant Unit No-1 in connection with prepardness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000688/2021-2022 | 129-YAAS/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 4.94 | 4.94 | 100 | 0
41 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Atkrishnarampur PH-2 W/S Scheme of DH-I Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000743/2021-2022 | 1510/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
42 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof pandal for continous safe storage of Drinking water pouches at Dakshin Roypur WTP under South 24 Pgs Mechanical Division, PHE Dte. From 17.05.2021 To 19.05.21 to combat super syclone YAAS. | Assistant Engineer -I | Junior Engineer | ORD/000724/2021-2022 | 1450/AE-II/SMD | 13/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.98 | 0.98 | 100 | 0
43 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to different locations for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000726/2021-2022 | 6/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
44 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000729/2021-2022 | 9/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
45 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000730/2021-2022 | 8/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
46 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Basulat PH-2 W/S Scheme of Falta Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000745/2021-2022 | 1521/A/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
47 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YASH at Diamond Harbour Hospital PH-1 W/S Scheme of D.H-I Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000746/2021-2022 | 1517/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
48 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000731/2021-2022 | 36/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
49 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & different areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000693/2021-2022 | 31/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
50 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing DG set at OHR No.-41 w/s scheme under Baruipur Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000700/2021-2022 | 72/YAAS/SMD | 26/05/2021 | 15/06/2021 | EMCON | 2.05 | 2.05 | 100 | 0
51 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing DG set at OHR No.-40 w/s scheme under Baruipur Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000701/2021-2022 | 71/YAAS/SMD | 26/05/2021 | 15/06/2021 | EMCON | 1.94 | 1.94 | 100 | 0
52 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000704/2021-2022 | 13/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.12 | 0.12 | 100 | 0
53 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000706/2021-2022 | 7/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
54 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000734/2021-2022 | 35/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
55 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & nearby areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000735/2021-2022 | 34/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.92 | 0.92 | 100 | 0
56 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at PH-3 of Amtali water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000669/2021-2022 | 22-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 3.46 | 3.46 | 100 | 0
57 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at OHR No-41 of Amtali water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000671/2021-2022 | 73-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 2.44 | 2.44 | 100 | 0
58 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at P.H No-2 O.H.R No-29 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000673/2021-2022 | 69/YASS/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 2.44 | 2.44 | 100 | 0
59 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000713/2021-2022 | 23/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
60 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at PH-I of Uttar kashinagar water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000747/2021-2022 | 92/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 0.81 | 0.81 | 100 | 0
61 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at PH-I, Zone-III of Nandakumarpur water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000748/2021-2022 | 89/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 1.18 | 1.18 | 100 | 0
62 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at PH-2 of Nagendrapur water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000750/2021-2022 | 84/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 0.96 | 0.96 | 100 | 0
63 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Running of Departmental 10 KVA DG set for running of Basanti PH-1, Zone-I MTU yard w/s scheme under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000795/2021-2022 | 792/SMSD | 11/06/2021 | 01/07/2021 | DEPALI CONSTRUCTION | 0.69 | 0.69 | 100 | 0
64 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at O.H.R No-32 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000677/2021-2022 | 70-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 2.44 | 2.44 | 100 | 0
65 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & several locations for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000716/2021-2022 | 16/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.9 | 0.9 | 100 | 0
66 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & several locations for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000718/2021-2022 | 20/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.41 | 0.41 | 100 | 0
67 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm roll fot pouch form form fill seal machine at D.Roypur Bottling Plant Unit NO-1 in connection with preparedness of cyclonic storm "YAAS" South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000721/2021-2022 | 100-YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.97 | 4.97 | 100 | 0
68 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply, delivery & storage of 10 HP fully Automatic Star Delta Starter at BS-II [Krishnamohan] Store under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000796/2021-2022 | 808/SMSD | 01/06/2021 | 21/06/2021 | EMCON | 1 | 1 | 100 | 0
69 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply, delivery & storage of Electrical Switch gear ancilliaries at BS-II [Krishnamohan] Store under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000797/2021-2022 | 793/SMSD | 01/06/2021 | 21/06/2021 | EMCON | 0.32 | 0.32 | 100 | 0
70 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at O.H.R No-48 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000679/2021-2022 | 77-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.44 | 2.44 | 100 | 0
71 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at OHR No-47 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000682/2021-2022 | 76Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.69 | 2.69 | 100 | 0
72 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Gunny bag D.Roypur Bottling Plant Unit No-1 in connection with prepardness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000686/2021-2022 | 97-YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 4.94 | 4.94 | 100 | 0
73 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof pandal for continous safe storage of Drinking water pouches at Dakshin Roypur WTP under South 24-Pgs Mechanical Division, PHE Dte. From 20.05.2021 to 22.05.21 to combat super cyclone YAAS. | Assistant Engineer -I | Junior Engineer | ORD/000723/2021-2022 | 1451/AE-II/SMD | 13/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.98 | 0.98 | 100 | 0
74 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply, delivery & storage of 10 HP fully Automatic Star Delta Starter at BS-II [Krishnamohan] Store under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000798/2021-2022 | 794/SMSD | 01/06/2021 | 21/06/2021 | EMCON | 0.9 | 0.9 | 100 | 0
75 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Kolkata & different areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000692/2021-2022 | 14/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
76 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000887/2021-2022 | 264/YAAS/SMSD | 17/06/2021 | 07/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
77 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000865/2021-2022 | 263/YAAS/SMSD | 16/06/2021 | 06/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
78 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000868/2021-2022 | 82/YAAS/SMSD | 24/05/2021 | 13/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
79 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000870/2021-2022 | 79/YAAS/SMSD | 24/05/2021 | 13/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
80 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000863/2021-2022 | 229/YAAS/SMSD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
81 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000867/2021-2022 | 42/YAAS/SMSD | 20/05/2021 | 09/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
82 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & installation of 20KVA Voltage stabilizer at PH No-1 of Basulat water supply scheme under S.24pgs Mechanical Division PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000911/2021-2022 | 1068/SMD | 14/09/2021 | 04/10/2021 | M/S. GHOSH ENTERPRISE | 3.16 | 3.16 | 100 | 0
83 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000876/2021-2022 | 121/YAAS/SMSD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
84 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Running of Departmental 15 KVA DG set for running of the pumping machinery at Sadhupur PH-2 w/s scheme under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000794/2021-2022 | 722/SMSD | 24/05/2021 | 13/06/2021 | DEPALI CONSTRUCTION | 0.37 | 0.37 | 100 | 0
85 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Yard lighting arrangement at PH-1 of Darikrishnanagar w/s scheme under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000841/2021-2022 | 593/SMD | 04/05/2021 | 24/05/2021 | GANGULY ENGINEERING CO. | 2.31 | 2.31 | 100 | 0
86 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to various locations to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000842/2021-2022 | 306/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
87 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Hasimnagar PH-2 W/S Scheme of Falta Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000742/2021-2022 | 1519/A/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
88 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to different locations to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000845/2021-2022 | 303/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
89 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Kanpur PH-1 W/S Scheme of DH-I Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000744/2021-2022 | 1518/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
90 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of lebel, Ink, make up, glue etc for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003233/2020-2021 | 329/SMD | 26/02/2021 | 18/03/2021 | J.D.J ENTERPRISE | 4.99 | 4.99 | 100 | 0
91 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003237/2020-2021 | 332/SMD | 26/02/2021 | 18/03/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
92 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches for MTU unit at Namkhana Block to combet YAAS - 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000848/2021-2022 | 301/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.81 | 0.81 | 100 | 0
93 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches for MTU unit at Patharpratima Block to combet YAAS - 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000849/2021-2022 | 302/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.71 | 0.71 | 100 | 0
94 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches for MTU unit at Kakdwip Block to combet YAAS - 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000850/2021-2022 | 299/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.88 | 0.88 | 100 | 0
95 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Rectification of outdoor and indoor lighting arrangement with allied works at Bansra and Kalaria W/S Scheme ( Block - Canning -I) under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000899/2021-2022 | 1185/SMSD | 13/09/2021 | 03/10/2021 | ROY & BISWAS ENGG. CO. | 0.63 | 0.63 | 100 | 0
96 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Installation & repairing of 7.5 HP Submersible pump motor set repairing of motor control panel at TW No- II of Dakshin Redokhali W/S Scheme under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000900/2021-2022 | 1333/SMSD | 07/12/2021 | 27/12/2021 | ROY & BISWAS ENGG. CO. | 0.49 | 0.49 | 100 | 0
97 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Providing hydrogen peroxide for whole body sanitizer tunnel and engagement of personnel for re-filling at the office of the Executive Engineer, Alipur Division PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000902/2021-2022 | 1858/AE-II/SMD | 23/07/2021 | 12/08/2021 | DEY ENTERPRISE | 0.82 | 0.82 | 100 | 0
98 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000853/2021-2022 | 123/YAAS/SMSD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
99 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & surrounding areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000727/2021-2022 | 15/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.33 | 0.33 | 100 | 0
100 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur bottling plant to Kolkata & surrounding areas for disaster YAAS under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000728/2021-2022 | 17/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.9 | 0.9 | 100 | 0
101 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches for MTU unit at Kakdwip Block to combet YAAS - 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000851/2021-2022 | 300/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.88 | 0.88 | 100 | 0
102 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000862/2021-2022 | 230/YAAS/SMSD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
103 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000881/2021-2022 | 110/YAAS/SMSD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
104 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000885/2021-2022 | 189/YAAS/SMSD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
105 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for hiring and running of DG set for providing back up power for BS-II Guest House in connection with GLAE-2021 under south 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000906/2021-2022 | 497/SMSD | 22/04/2021 | 12/05/2021 | DEY ENTERPRISE | 0.5 | 0.5 | 100 | 0
106 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000855/2021-2022 | 87/YAAS/SMSD | 25/05/2021 | 14/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
107 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000858/2021-2022 | 108/YAAS/SMSD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
108 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for supply and delivery of PET perform(500ML) for packaged drinking water bottling plant at BS-II under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003289/2020-2021 | 2522/SMD | 04/09/2020 | 24/09/2020 | J.D.J ENTERPRISE | 4.75 | 4.75 | 100 | 0
109 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of shrink film for D.Roypur Bottling Plant Unit-2 in connection with ensuing West Bengal Assembly General Election 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003291/2020-2021 | 331/SMD | 26/02/2021 | 18/03/2021 | J.D.J ENTERPRISE | 4.98 | 0.19 | 3.84 | 0
110 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply, delivery, fitting, fixing of Ceiling fan and other allied works at different W/S Scheme of (Block-Canning -I & Bhangar-II) under South 24pgs Mechanical Division , PHE DTe. | Assistant Engineer -I | Junior Engineer | ORD/000894/2021-2022 | 962/SMSD | 23/07/2021 | 12/08/2021 | ROY & BISWAS ENGG. CO. | 0.89 | 0.89 | 100 | 0
111 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Replacement of Sluice valve, Non return valves and other allied works at Pump House no. 4 of Dharmatala W/S Scheme (Block - Canning - I ) Under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000898/2021-2022 | 961/SMSD | 23/07/2021 | 12/08/2021 | ROY & BISWAS ENGG. CO. | 0.3 | 0.3 | 100 | 0
112 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and Installation of 20KVA voltage stabilizer at PH N0-5 of D.H Municipality Aug. water supply scheme under S.24 pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000901/2021-2022 | 1066/SMD | 14/09/2021 | 04/10/2021 | ROY & BISWAS ENGG. CO. | 3.2 | 3.2 | 100 | 0
113 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000872/2021-2022 | 217/YAAS/SMSD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
114 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000873/2021-2022 | 216/YAAS/SMSD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
115 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Providing hydrogen peroxide for whole body sanitizer tunnel and engagement of personnel for re-filling at the office of the Executive Engineer, South 24-Pgs water supply Division-I PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000904/2021-2022 | 1856/AE-II/SMD | 23/07/2021 | 12/08/2021 | DEY ENTERPRISE | 0.82 | 0.82 | 100 | 0
116 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for hiring and running of DG set for providing back up power for BS-II Guest House in connection with GLAE-2021 under south 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000905/2021-2022 | 475/SMSD | 16/04/2021 | 06/05/2021 | DEY ENTERPRISE | 0.52 | 0.52 | 100 | 0
117 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for hiring and running of DG set for providing back up power for BS-II Guest House in connection with GLAE-2021 under south 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000907/2021-2022 | 448/SMSD | 10/04/2021 | 30/04/2021 | DEY ENTERPRISE | 0.5 | 0.5 | 100 | 0
118 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003235/2020-2021 | 398/SMD | 16/03/2021 | 05/04/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
119 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000835/2021-2022 | 215/YAAS/SMSD | 07/06/2021 | 22/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
120 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000837/2021-2022 | 262/YAAS/SMSD | 15/06/2021 | 30/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
121 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000838/2021-2022 | 175/YAAS/SMSD | 02/06/2021 | 17/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
122 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000839/2021-2022 | 192/YAAS/SMSD | 04/06/2021 | 19/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
123 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Rectification of 3 (Three) No Voltage correction devices of Bhaleya (P/H No. 1), Banibada Belekhali (P/H No.III) & Bansra (P/H No. i, Zone- I), W/S Scheme and 2 (TWO) nos. Motor Control Panel of Bhaleya (P/H No.1) and Banibada Belekhali (P/H No. III)W/S Scheme (Block - Canning - I)Under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000897/2021-2022 | 1271/SMSD | 29/10/2021 | 18/11/2021 | ROY & BISWAS ENGG. CO. | 0.66 | 0.66 | 100 | 0
124 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Renovation of illumination arrangement for OHR No-8 under South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000908/2021-2022 | 1921/AE-II/SMD | 16/08/2021 | 05/09/2021 | SHIVAM ENTERPRISE | 1.01 | 0.66 | 65.02 | 0
125 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Lifting of Tubewell height and allied works at Hasimnagar PH No-1 W/S Scheme under south 24pgs Mechanical Diviion PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000909/2021-2022 | 1963/AE-II/SMD | 19/08/2021 | 08/09/2021 | SHIVAM ENTERPRISE | 0.66 | 1.05 | 159.77 | 0
126 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to surrounding areas to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000843/2021-2022 | 305/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
127 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Contionuation order for Supply & delivery of polyfilm roll for MTU at Basanti in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003231/2020-2021 | 391/SMD. | 10/03/2021 | 30/03/2021 | J.D.J ENTERPRISE | 4.99 | 4.99 | 100 | 0
128 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to different locations to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000847/2021-2022 | 307/AE-I/SMD. | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.55 | 0.55 | 100 | 0
129 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000856/2021-2022 | 89/YAAS/SMSD | 25/05/2021 | 14/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
130 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000857/2021-2022 | 107/YAAS/SMSD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
131 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000860/2021-2022 | 218/YAAS/SMSD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
132 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000861/2021-2022 | 228/YAAS/SMSD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
133 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000864/2021-2022 | 231/YAAS/SMSD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
134 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000866/2021-2022 | 38/YAAS/SMSD | 20/05/2021 | 09/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
135 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000869/2021-2022 | 83/YAAS/SMSD | 24/05/2021 | 13/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
136 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000871/2021-2022 | 85/YAAS/SMSD | 25/05/2021 | 14/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
137 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000878/2021-2022 | 122/YAAS/SMSD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
138 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000879/2021-2022 | 265/YAAS/SMSD | 17/06/2021 | 07/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
139 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000882/2021-2022 | 178/YAAS/SMSD | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
140 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000886/2021-2022 | 120/YAAS/SMSD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
141 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for supply and delivery of PET perform for D.Roypur Bottling Plant Unit-2 in connection with ensuing West Bengal Assembly General Election 2021 under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003290/2020-2021 | 341/SMD | 01/03/2021 | 21/03/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
142 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000829/2021-2022 | 165/YAAS/SMSD | 01/06/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
143 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000832/2021-2022 | 182/YAAS/SMSD | 03/06/2021 | 18/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
144 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000880/2021-2022 | 24/YAAS/SMSD | 18/05/2021 | 07/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
145 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000884/2021-2022 | 188/YAAS/SMSD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
146 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000888/2021-2022 | 23/YAAS/SMSD | 18/05/2021 | 07/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
147 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000830/2021-2022 | 214/YAAS/SMSD | 07/06/2021 | 22/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
148 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000831/2021-2022 | 191/YAAS/SMSD | 04/06/2021 | 19/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
149 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000833/2021-2022 | 174/YAAS/SMSD | 02/06/2021 | 17/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
150 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000834/2021-2022 | 164/YAAS/SMSD | 01/06/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
151 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at BS-II temporary pouch production area under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000836/2021-2022 | 183/YAAS/SMSD | 03/06/2021 | 18/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
152 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for Supply and delivery of gunny bags for emergency carriage of drinking water pouch for in connection with YAAS at Basanti MTU yard under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000840/2021-2022 | 261/YAAS/SMSD | 15/06/2021 | 30/06/2021 | S.P. CONSTRUCTION | 0.99 | 0.99 | 100 | 0
153 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply,fitting fixing and laying submersible cable at MOSAT P/H No-2 under SMD,PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000910/2021-2022 | 2159/AE-II/SMD | 16/09/2021 | 06/10/2021 | SHIVAM ENTERPRISE | 1.05 | 1.93 | 183.07 | 0
154 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003234/2020-2021 | 384/SMD | 10/03/2021 | 30/03/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
155 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003236/2020-2021 | 452/SMD | 19/03/2021 | 08/04/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
156 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Cap for at D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003239/2020-2021 | 330/SMD | 26/02/2021 | 18/03/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
157 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Rectification of 4 (Four) Nos Motor Control of (P/H No. 2 & 3 of Dharmatala, P/H NO-4 of Moukhali & P/H No 3 of Uttar Anadhberia W/S Scheme) different water supply scheme ( BLock Canning -I) Under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000895/2021-2022 | 1077/SMSD | 24/08/2021 | 13/09/2021 | ROY & BISWAS ENGG. CO. | 0.41 | 0.41 | 100 | 0
158 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Withdrawing and installation of pumping machinery and other allied works at Pump House No. 2 of Dharmatala W/S scheme under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000896/2021-2022 | 1064/SMSD | 17/08/2021 | 06/09/2021 | ROY & BISWAS ENGG. CO. | 0.13 | 0.13 | 100 | 0
159 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Providing hydrogen peroxide for whole body sanitizer tunnel and engagement of personnel for re-filling at the office of the Executive Engineer, Alipur Division PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000903/2021-2022 | 1857/AE-II/SMD | 23/07/2021 | 12/08/2021 | DEY ENTERPRISE | 0.82 | 0.82 | 100 | 0
160 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for hiring and running of DG set for providing back up power for BS-II Guest House in connection with GLAE-2021 under south 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003241/2020-2021 | 409/SMSD | 27/03/2021 | 16/04/2021 | DEY ENTERPRISE | 0.51 | 0.51 | 100 | 0
161 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of gunny bags for emergency carriage of drinking water pouch for Combat YAAS under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/002494/2021-2022 | 6/YAAS/I/SMSD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.91 | 0.56 | 62.06 | 0
162 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Continuation order for supply and delivery of PET perform for Rana Paschim Ramnagar Bottling plant under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/001033/2021-2022 | 684/SMD | 03/06/2021 | 23/06/2021 | J.D.J ENTERPRISE | 4.95 | 4.95 | 100 | 0
163 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000877/2021-2022 | 109/YAAS/SMSD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
164 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000875/2021-2022 | 193/YAAS/SMSD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
165 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000883/2021-2022 | 184/YAAS/SMSD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
166 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of self contained water pouches to different locations to combet with Cyclone YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000844/2021-2022 | 304/AE-I/SMD | 18/05/2021 | 02/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
167 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Carriage of Packaged drinking water from Dakshin Roypur Bottling Plant to Gosaba Block & nearby areas for disaster YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000708/2021-2022 | 21/YAAS/AE-II/SMD | 17/05/2021 | 06/06/2021 | M/S. S.S. ENTERPRISE | 0.91 | 0.91 | 100 | 0
168 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont order for Supply and delivery of Polyfilm roll fot pouch form form fill seal machine at D.Roypur Bottling Plant Unit NO-1 in connection with preparedness of cyclonic storm "YAAS" South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000722/2021-2022 | 144-YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.97 | 4.97 | 100 | 0
169 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Contionuation order for Supply & delivery of Pet preform for D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003232/2020-2021 | 513/SMD | 30/03/2021 | 19/04/2021 | J.D.J ENTERPRISE | 4.98 | 4.98 | 100 | 0
170 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing diesel generator set at P.H No-1 O.H.R No-29 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supplyas and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000678/2021-2022 | 68/YASS/SMD | 26/05/2021 | 15/06/2021 | S.K. ENTERPRISE | 2.44 | 2.44 | 100 | 0
171 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Providing DG set at PH-1 of Uttar Kashinagar w/s scheme under Baruipur Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000699/2021-2022 | 93/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. PS & ASSOCIATES | 1.62 | 1.62 | 100 | 0
172 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000854/2021-2022 | 27/YAAS/SMSD | 18/05/2021 | 07/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
173 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Rectification of 4 (Four) Nos Voltage correction devices of Andhia (P/H No. 2), Moukhali (P/H No.2), Bhogali (P/H No. 2), Dharmatala (P/H No. 2) W/S Scheme and minor rectification of motor control at Andhia (P/H No. 2) W/S Scheme Under SMD PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000893/2021-2022 | 1309/SMSD | 17/11/2021 | 07/12/2021 | ROY & BISWAS ENGG. CO. | 0.64 | 0.64 | 100 | 0
174 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply & delivery of Vaccum Drum for Hotmelt Labeller m/c at D.Roypur Bottling Plant Unit no.2 in connection with ensuing West Bengal Assembly General Election 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/003230/2020-2021 | 403/SMD | 16/03/2021 | 05/04/2021 | J.D.J ENTERPRISE | 4.99 | 4.99 | 100 | 0
175 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000874/2021-2022 | 25/YAAS/SMSD | 18/05/2021 | 07/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
176 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Supply and delivery of Polyfilm for emergency production of drinking water pouches to commet of cyclonic storm YAAS at Basanti MTU under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000859/2021-2022 | 111/YAAS/SMSD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
177 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Stationery Goods |  |  | VCH/003722/2021-2022 | 62/PFMS | 21/02/2022 | 21/02/2022 | BARRACKPORE CENTRAL ZONE WHOLESALE CONSUMERS' CO-OPERATIVE SOCIETY LTD. | 1.96 | 0 | 0 | 0
178 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Fuel Bills |  |  | VCH/000200/2022-2023 | 16/PFMS | 18/04/2022 | 18/04/2022 | TEMPLE MOTORS | 1.7 | 0 | 0 | 0
179 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Kakdwip, Sagar, Namkhana & Patharpratima Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09032 | Disaster | Cont. order for supply and delivery of Gunny bag at Sagar Island in connection with preparedness of cyclonic strom YAAS under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer -I | Junior Engineer | ORD/000696/2021-2022 | 155/YAAS/SMD | 29/05/2021 | 18/06/2021 | S.P. CONSTRUCTION | 4.94 | 0 | 0 | 0
Total | [13 empty] | 295.18 | 254.19 | 86.11