## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Buita W/S Scheme for Booth No:141 to 144 and Adjoining Areas under Budge Budge-I Block | SM/07017 | Retrofitting | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 141 to 144 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000362/2020-2021 | 1411/SWD-I | 14/12/2020 | 13/04/2021 | BANIK BROTHERS | 94.35 | 88.77 | 94.09 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Buita W/S Scheme for Booth No:141 to 144 and Adjoining Areas under Budge Budge-I Block | SM/07017 | Retrofitting | Retrofitting of distribution system by extension of pipeline for Buita W/S Scheme for Booth No - 141 to 144 and adjoining areas under Budge Budge-I Block with allied works unuder South 24-Parganas W/S Divn-I, P.H.E. Dte, South 24-Pgns District. |  |  | ORD/000586/2021-2022 | 1471/SWD-I | 15/12/2021 | 29/01/2022 | BANIK BROTHERS | 2.54 | 2.54 | 100 | 100
Total | [13 empty] | 96.89 | 91.31 | 94.24