## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Nandarampur W/S Scheme for Chak Nabashan Mouza and adjoining areas under Budge Budge-I Block | SM/07019 | Retrofitting | Retrofitting of distribution system for Nandarampur W/S Scheme for ChakNabashan Mouza and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000102/2020-2021 | 1273/SWD-I | 23/11/2020 | 23/03/2021 | NIRMAL UDYOG | 25.27 | 24.42 | 96.66 | 0
Total | [13 empty] | 25.27 | 24.42 | 96.66