## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works | SM/07050 | Retrofitting | Retrofitting of distribution system for Uttar Roypur W/S Scheme forUttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with alliedworks under SWD - I, P.H.E. Dte District South 24 Parganas | AE SWSD-I |  | ORD/000328/2020-2021 | 1396/SWD-I JJM | 11/12/2020 | 10/04/2021 | SRIJON ENTERPRISE | 85.74 | 25.57 | 29.83 | 60
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works | SM/07050 | Retrofitting | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Uttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000117/2020-2021 | 1396/SWD-I | 11/12/2020 | 10/04/2021 | SRIJON ENTERPRISE | 86.18 | 57.87 | 67.15 | 60
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Uttar Roypur Balarampur (Part), Chak Nabashan (Part) Mouza under Budge Budge-I Block with allied works | SM/07050 | Retrofitting | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6136) PART-IV | AE SWSD-I | JE-1 | ORD/000463/2022-2023 | 2773/SWD-I | 31/01/2023 | 02/03/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 3.07 | 3.06 | 99.57 | 100
Total | [13 empty] | 175 | 86.5 | 49.43