## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection for Atmarampur W/S Scheme for Atmarampur,Chingripota and Santoshpur Mouza under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur. | SM/07051 | Retrofitting | Providing Functional household Tap Connection by retrofitting of Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza under Budge Budge I Block with allied works under " Surface water Based Mega water Supply Scheme for Falta Mathurapur" | AE SWSD-I |  | ORD/000111/2020-2021 | 1358/SWD-I | 08/12/2020 | 07/04/2021 | M/S. S.S. ENTERPRISE | 97.1 | 76.44 | 78.73 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection for Atmarampur W/S Scheme for Atmarampur,Chingripota and Santoshpur Mouza under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur. | SM/07051 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Atmarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6114) Part -I | AE SWSD-I |  | ORD/000471/2022-2023 | 2783/SWD-I | 31/01/2023 | 17/03/2023 | R.D CONSTRUCTION | 2.86 | 0 | 0 | 100
Total | [13 empty] | 99.95 | 76.44 | 76.48