## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur | SM/07052 | Retrofitting | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ | AE SWSD-I |  | ORD/000329/2020-2021 | 1464/SWD-I JJM | 21/12/2020 | 20/04/2021 | M/S. GOUTAM ROY | 66.37 | 15.09 | 22.74 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur | SM/07052 | Retrofitting | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ |  |  | ORD/000115/2020-2021 | 1464/SWD-I | 21/12/2020 | 20/04/2021 | M/S. GOUTAM ROY | 66.54 | 55.28 | 83.08 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection for Betuabati W/S Scheme under Budge Budge-I Block with allied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur | SM/07052 | Retrofitting | Balance work of Providing Functional Household Tap Connection for Bethuabati W/S Scheme & Adjoining Areas under Budge Budge-I block with alied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur under South-24 Pns W/S- Divn-I, PHE Dte. | AE SWSD-I |  | ORD/000328/2022-2023 | 2045/SWD-I | 30/11/2022 | 29/01/2023 | P.S. AND ASSOCIATES | 20.98 | 20.84 | 99.31 | 35
Total | [13 empty] | 153.89 | 91.21 | 59.27