## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works | SM/07054 | Retrofitting | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Booth No: 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000108/2020-2021 | 1360/SWD-I | 08/12/2020 | 07/04/2021 | CALCON CONSTRUCTIONS | 96.86 | 178.74 | 184.54 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Uttar Roypur W/S Scheme for Booth No:145 to 152 under Budge Budge-I Block with allied works | SM/07054 | Retrofitting | Balance repair of Bitumen Road damaged due to laying of pipeline of within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6133) PART-V | AE SWSD-I | JE-1 | ORD/000464/2022-2023 | 2774/SWD-I | 31/01/2023 | 02/03/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 2.41 | 2.36 | 97.97 | 100
Total | [13 empty] | 99.27 | 181.11 | 182.44