## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works | SM/07055 | Retrofitting | Retrofitting of distribution system for Nandarampur W/S Scheme for Booth 170 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000116/2020-2021 | 1394/SWD-I | 11/12/2020 | 10/04/2021 | PROJECT AND MAINTENANCE | 92.1 | 10.62 | 11.54 | 90
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works | SM/07055 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6127) Part -H | AE SWSD-I |  | ORD/000470/2022-2023 | 2782/SWD-I | 31/01/2023 | 17/03/2023 | R.D CONSTRUCTION | 2.51 | 4.73 | 188.88 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of distribution System For Moukhali W/S Scheme for Durgapur Moukhali and Jagatballavpur under Budge Budge-I Block with allied works | SM/07055 | Retrofitting | Retrofitting of distribution system for Moukhali W/S Scheme for Durgapur Moukhali and Jagat Ballavpur under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000309/2020-2021 | 1414/SWD- I | 14/12/2020 | 13/04/2021 | SUPRITI ENTERPRISE | 96.89 | 6.17 | 6.37 | 100
Total | [13 empty] | 191.51 | 21.53 | 11.24