## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Pratapnagar, Sonarpur-II (Part-I), Sonarpur-II (Part-II) G.P.s of Sonarpur Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000242/2021-2022 | BP-2021-22-70 | 06/08/2021 |  | M/S. JAYDEEP DASGUPTA | 2.84 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Kalikapur-II, Kamrabad & Kheadah-I G.P.s of Sonarpur Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000241/2021-2022 | BP-2021-22-69 | 06/08/2021 |  | M/S. JAYDEEP DASGUPTA | 3.72 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Bonhooghly-I, Bonhooghly-II & Kalikapur-I G.P.s of Sonarpur Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas |  |  | VCH/000243/2021-2022 | BP-2021-22-71 | 06/08/2021 |  | M/S. JAYDEEP DASGUPTA | 2.98 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Kheadah-II (Part-I), Kheadah-II (Part-II), Langal Beria & Polghat G.P.s of Sonarpur Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000244/2021-2022 | BP-2021-22-72 | 06/08/2021 |  | M/S. JAYDEEP DASGUPTA | 2.13 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Chandaneswar-II, Durgapur (Part-I), Durgapur (Part-II) & Jagulgachi (Part-II) G.P.s of Bhangar-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000348/2021-2022 | BP-2021-22-104 | 17/08/2021 |  | J.D. CONSTRUCTION | 3.41 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Bodra (Part-I), Bodra (Part-II), Chandaneswar-I & Tardaha (Part-II) G.P.s of Bhangar-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000350/2021-2022 | BP-2021-22-106 | 17/08/2021 |  | J.D. CONSTRUCTION | 4.11 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Narayanpur (Part-I), Narayanpur (Part-II), Pranganj (Part-II) & Tardaha (Part-I) G.P.s of Bhangar-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000351/2021-2022 | BP-2021-22-107 | 17/08/2021 |  | J.D. CONSTRUCTION | 3.14 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Sonarpur & Bhangar-I blocks. | SM/08060 | Support-M&E | Functional Household Tap Connection door to door survey for Jagulgachi (Part-I), Pranganj (Part-I) & Sanksahar G.P.s of Bhangar-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000349/2021-2022 | BP-2021-22-105 | 17/08/2021 |  | J.D. CONSTRUCTION | 2.61 | 0 | 0 | 0
Total | [13 empty] | 24.93 | 0 | 0