## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Chandanpukur, Bagdaha, Dhanberia & Durgapur mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08180 | Retrofitting | Interconnection including laying distribution system from Big dia Tube well covering Chandanpukur, Bagdaha, Dhanberia, Durgapur & Gazipur mouzas for improvement of water supply & Providing functional house hold tap connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000303/2020-2021 | 2132/SWD-I | 26/02/2021 | 26/06/2021 | ALOK ENTERPRISE | 169.36 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Chandanpukur, Bagdaha, Dhanberia & Durgapur mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08180 | Retrofitting | Restoration of damages due to laying of water-line by PHE Directorate at Durgapur Station Road to Hotor and Mahespur connecting Road from 0.0 Km to 2.4 Km under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.65,08,952/- x 50% = Rs.32,54,476/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. |  |  | BILL/00564/2023-2024 | BP-2023-24-266 | 25/08/2023 | 25/08/2023 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 32.54 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Chandanpukur, Bagdaha, Dhanberia & Durgapur mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08180 | Retrofitting | Protection work by drum sheet walling on Sal-bullah / Eucaliptus bullah piling for protection of rising main at chandanpukur site of shikharbali-II G.P under Baruipur Sub-Division of South24-Pgns, W/S Division-I, P.H.E.Dte. | AE BSD | JE-1 | ORD/000996/2022-2023 | 1079/SWD-I | 16/08/2022 | 31/08/2022 | MONDAL CONSTRUCTION (BARUIPUR) | 1.18 | 0 | 0 | 100
Total | [13 empty] | 203.08 | 0 | 0