## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08181 | Retrofitting | Improvement of water supply by Interconnection from existing Big dia tube well and laying distribution system with CIDF, UPVC pipes Including providing Functional House Hold Tap Connection by retrofitting of scheme ¿Improvement of water supply [Phase-III] in Baruipur and Mograhat-II block¿ of Sankarpur-II GP within zone-43, covering Nur, Durgo, Balbalia, Surjopur hat mouzas under surface water based water supply scheme for arsenic affected areas of south 24- Parganas district. | AE BSD |  | ORD/000071/2021-2022 | 479 /SWD-I JJM p | 07/07/2021 | 04/11/2021 | M/S. S.S. ENTERPRISE | 193.14 | 2.58 | 1.34 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08181 | Retrofitting | Interconection including laying distribution system from Big dia Tube well covering Kundarali, Mamudpur & Indraballa for improvement of water supply & Providing Functional House Hold Tap Connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000295/2020-2021 | 2131/SWD-I | 26/02/2021 | 26/06/2021 | PEECON | 203.09 | 153.23 | 75.45 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08181 | Retrofitting | Restoration of damages due to laying of water-line by PHE Directorate at Sashan Station to Durgapur station connecting road from 0.000 kmp 0.830kmp under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.38,91,559/- x 50% = Rs.19,45,780/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. |  |  | BILL/00562/2023-2024 | BP-2023-24-266 | 25/08/2023 | 25/08/2023 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 19.46 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of W/S including providing FHTC for Kundarali, Mamudpur & Indrapala mouza of Sikharbali-II GP, Baruipur-II Block in the district of South 24 Parganas. | SM/08181 | Retrofitting | Restoration of damages due to laying of water-line by PHE Directorate at Kalyanpur - Indralala - Durgapur Station Road from 0.000 kmp to 3.15 km (R/S: 230m & L/S: 1520m) under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.73,16,902/- x 50% = Rs.36,58,451/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. |  |  | BILL/00563/2023-2024 | BP-2023-24-266 | 25/08/2023 | 25/08/2023 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 36.58 | 0 | 0 | 0
Total | [13 empty] | 452.27 | 155.81 | 34.45