## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of MS Steel Plate Flooring in old intake of 34MGD at Dongaria in connection with Surface Water based Water Supply Scheme for Arsenic affected areas of South 24 Parganas in connection to destruction by 'Aumfun' |  |  | ORD/000276/2020-2021 | 1071/SWD-I | 08/10/2020 | 22/11/2020 | DIAMOND ENTERPRISE | 5.9 | 5.89 | 99.77 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply and Ancillary works From the Source of BS-I to Begam pur High School of Zone-28 (BegamPur) Under Baruipur Block due to Cyclone "AMPHAN 2020 " under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | ORD/000348/2020-2021 | 771/SWD-I | 14/08/2020 | 28/09/2020 | M/S. GOUTAM ROY | 4.4 | 4.39 | 99.87 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply and Ancillary works from N.P.- 107-108 of Zone-28 of Baruipur Block due to Cyclone "AMPHAN 2020 " under Surface Water Based Water Supply Scheme for Arsenic Effected Areas of South 24 Paraganas Dist. |  |  | ORD/000349/2020-2021 | 743/SWD-I | 14/08/2020 | 28/09/2020 | M/S. GOUTAM ROY | 4.76 | 4.76 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of worn out columns, Girders with allied components of old intake of 34MGD at Dongaria in connection with Surface Water based Water Supply Scheme for Arsenic affected areas of South 24 Parganas in connection to destruction by 'Aumfun' |  |  | ORD/000372/2020-2021 | 1072/ SWD-I | 08/10/2020 | 22/11/2020 | M/S. S.S. ENTERPRISE | 25.67 | 2.05 | 7.98 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Re-construction of boundary wall of Zone-45, Mograhat-II block which is damaged due to Cyclone "AMPHAN 2020? under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000369/2020-2021 | 851/SWD-I | 03/09/2020 | 18/10/2020 | M/S. GOUTAM ROY | 12.13 | 11.52 | 94.95 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 63-62 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | ORD/000381/2020-2021 | 590/SWD-I | 22/07/2020 | 05/09/2020 | M/S. KUNDU CONSTRUCTION | 4.08 | 3.15 | 77.05 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of service road maintained by KMDA due to restoration of UPVC pipe line (90 mm & 110 mm) dia damaged due to super cyclone AMPHAN 2020 within Zone-25 of Baruipur block under "Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas district". |  |  | ORD/000058/2020-2021 | 1496/SWD-I | 30/12/2020 | 29/01/2021 | LAKSHMI NARAYAN SAHOO | 1.22 | 1.21 | 98.92 | 0
Total | [13 empty] | 58.17 | 32.97 | 56.67