## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | SM/09944 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000085/2021-2022 | 1162/SWD-I JJM | 02/11/2021 | 02/03/2022 | UNICON INDIA | 125.43 | 26.28 | 20.95 | 25
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | SM/09944 | Retrofitting | Balance of Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD,AE SWSD-I | JE-1 | ORD/000040/2022-2023 | 978/SWD-I | 27/07/2022 | 04/01/2025 | CALCON CONSTRUCTIONS | 75.21 | 18.82 | 25.02 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | SM/09944 | Retrofitting | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 8300 ) PART-I | AE SWSD-I | JE-1 | ORD/000459/2022-2023 | 2771/SWD-I | 31/01/2023 | 02/03/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 8.53 | 8.52 | 99.83 | 100
Total | [13 empty] | 209.17 | 53.62 | 25.64