## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09945 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I | JE-1 | ORD/000089/2021-2022 | 1163/SWD-I JJM | 02/11/2021 | 02/03/2022 | CALCON CONSTRUCTIONS | 137.48 | 64.94 | 47.23 | 10
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09945 | Retrofitting | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Divn. - I P.H.E Dte. (TSM/8301) PART-II | AE SWSD-I | JE-1 | ORD/000455/2022-2023 | 2730/SWD-I | 27/01/2023 | 26/02/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 23.13 | 23.08 | 99.76 | 100
Total | [13 empty] | 160.62 | 88.02 | 54.8