## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09949 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD,AE SWSD-I | JE-1 | ORD/000077/2021-2022 | 1104/SWD-I JJM | 25/10/2021 | 22/02/2022 | J.D. CONSTRUCTION | 90.16 | 88.67 | 98.35 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09949 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Jamalpur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8294) Part - B | AE SWSD-I |  | ORD/000454/2022-2023 | 2729/SWD-I | 27/01/2023 | 13/03/2023 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 9.53 | 9.53 | 99.91 | 100
Total | [13 empty] | 99.69 | 98.2 | 98.5