## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09950 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000079/2021-2022 | 1202/SWD-I JJM | 25/10/2021 | 22/02/2022 | SUPRITI ENTERPRISE | 82.17 | 20.66 | 25.14 | 60
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09950 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Moukhali W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8295) Part -C | AE SWSD-I |  | ORD/000460/2022-2023 | 2778/SWD-I | 31/01/2023 | 17/03/2023 | RIDIP ENTERPRISE | 7.14 | 7.14 | 99.96 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09950 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000037/2021-2022 | 1102/SWD-I | 25/10/2021 | 22/02/2022 | SUPRITI ENTERPRISE | 82.25 | 45.08 | 54.8 | 100
Total | [13 empty] | 171.57 | 72.87 | 42.47