## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | SM/09951 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000081/2021-2022 | 1106/SWD-I JJM | 25/10/2021 | 22/02/2022 | M/S. JAYDEEP DASGUPTA | 82.35 | 48.58 | 58.99 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte | SM/09951 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nischintipur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8297) Part - A | AE SWSD-I |  | ORD/000468/2022-2023 | 2777/SWD-I | 31/01/2023 | 02/03/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 8.58 | 8.53 | 99.43 | 75
Total | [13 empty] | 90.93 | 57.11 | 62.8