## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09954 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000078/2021-2022 | 1204/SWD-I JJM | 09/11/2021 | 09/03/2022 | VISHAL CONSTRUCTION CO. | 254.11 | 250.68 | 98.65 | 100
Total | [13 empty] | 254.11 | 250.68 | 98.65