## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09955 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte. District South 24 Parganas. | AE SWSD-I |  | ORD/000088/2021-2022 | 1205/SWD-I | 09/11/2021 | 09/03/2022 | SATYABRATA CHAKRABORTY | 268.77 | 148.17 | 55.13 | 60
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09955 | Retrofitting | Balance repair of Bitumen Road damaged due to laying of pipeline within Buita W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM/ 8292 ) PART-VII | AE SWSD-I | JE-1 | ORD/000456/2022-2023 | 2728/SWD-I | 27/01/2023 | 26/02/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 18.68 | 15.65 | 83.81 | 100
Total | [13 empty] | 287.45 | 163.82 | 56.99