## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (8 Nos. Model-2) (Group-11) | AE SWSD-II |  | ORD/000193/2021-2022 | 2237/SWD-I | 15/02/2022 | 01/04/2022 | SUKALPA NIRMAN | 14.26 | 11.21 | 78.64 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-3 and 2 Nos. Model-4) (Group-12) | AE SWSD-II |  | ORD/000255/2021-2022 | 2268/SWD-I | 15/02/2022 | 01/04/2022 | SANJAY MIDDEY | 7.41 | 5.06 | 68.31 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 2 Nos. Model-6) (Group-1) | AE SWSD-II |  | ORD/000262/2021-2022 | 2252/SWD-I | 15/02/2022 | 01/04/2022 | ADRIK ENTERPRISE | 10.64 | 7.95 | 74.75 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (17 Nos. Model-6) (Group-14) | AE SWSD-II |  | ORD/000274/2021-2022 | 2200/SWD-I | 15/02/2022 | 16/04/2022 | SRIJON ENTERPRISE | 45 | 43.11 | 95.79 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (9 Nos. Model-6) (Group-17) | AE SWSD-II |  | ORD/000304/2021-2022 | 2217/SWD-I | 15/02/2022 | 01/04/2022 | NIRMAL UDYOG | 22.83 | 21.98 | 96.26 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-5 and 1 No. Model-7) (Group-13) | AE SWSD-II |  | ORD/000252/2021-2022 | 2258/SWD-I | 15/02/2022 | 01/04/2022 | SOMNATH ENTERPRISE | 8.44 | 5.48 | 64.86 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (21 Nos. Model-6) (Group-16) | AE SWSD-II |  | ORD/000276/2021-2022 | 2190/SWD-I | 15/02/2022 | 16/04/2022 | RAJLAXMI CONSTRUCTION | 55.6 | 51.02 | 91.77 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (31 Nos. Model-6) (Group-6) | AE SWSD-II |  | ORD/000303/2021-2022 | 2175/SWD-I | 15/02/2022 | 16/04/2022 | NIRMAL UDYOG | 82.1 | 81.5 | 99.27 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (22 Nos. Model-6) (Group-2) |  |  | ORD/000577/2021-2022 | 2188/SWD-I | 15/02/2022 | 16/04/2022 | MANAS CHATTERJEE | 58.26 | 19.05 | 32.7 | 100
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 10 Nos. Model-6) (Group-15) |  |  | ORD/000581/2021-2022 | 2210/SWD-I | 15/02/2022 | 16/04/2022 | NILKAMAL BASAK | 31.79 | 13.31 | 41.87 | 80
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 2103/SWD-I | 11/02/2022 |  | Resource Division | 321.23 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (33 Nos. Model-6) (Group-5) | AE SWSD-II | JE2 | ORD/000415/2021-2022 | 2171/SWD-I | 15/02/2022 | 16/04/2022 | MS SARADA UDYOG | 87.36 | 38.79 | 44.41 | 70
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 6 Nos. Model-6) (Group-10) | AE SWSD-II | JE4 | ORD/000592/2021-2022 | 2223/SWD-I | 15/02/2022 | 01/04/2022 | J. ENTERPRISE | 21.24 | 10.04 | 47.27 | 98
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-6) (Group-9) | AE SWSD-II | JE2 | ORD/000594/2021-2022 | 2231/SWD-I | 15/02/2022 | 01/04/2022 | ELECTRONIC SURVILLANCE | 15.9 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-7 and 2 Nos. Model-8) (Group-3) | AE SWSD-II | JE2 | ORD/000593/2021-2022 | 2225/SWD-I | 15/02/2022 | 01/04/2022 | M/S. FAIZUL HAQUE BISWAS | 18.83 | 7.84 | 41.66 | 80
16 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7 and 14 Nos. Model-6) (Group-4) | AE SWSD-II | JE1 | ORD/000412/2021-2022 | 2203/SWD-I | 15/02/2022 | 15/06/2022 | NIRMAL UDYOG | 39.76 | 17.93 | 45.09 | 97
Total | [13 empty] | 840.63 | 334.26 | 39.76