## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (20 Nos. Model-6) (Group-24) [2nd Call] | AE BSD,AE SWSD-I | JE-1 | ORD/000011/2022-2023 | 857/SWD-I | 12/07/2022 | 10/09/2022 | MS KRISHNA MONDAL | 52.52 | 46.46 | 88.47 | 95
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (27 Nos. Model-6) (Group-21) | AE BSD,AE SWSD-I |  | ORD/000253/2021-2022 | 2183/SWD-I | 15/02/2022 | 16/04/2022 | MONDAL CONSTRUCTION | 71.44 | 59.46 | 83.24 | 85
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (15 Nos. Model-6) (Group-23) | AE BSD,AE SWSD-I |  | ORD/000384/2021-2022 | 2204/SWD-I | 15/02/2022 | 16/04/2022 | P S CONSTRUCTION | 39.7 | 28.48 | 71.75 | 75
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-7) (Group-22) | AE BSD |  | ORD/000410/2021-2022 | 2276/SWDI | 15/02/2022 | 01/04/2022 | DEY CONSTRUCTION | 5.35 | 5.01 | 93.62 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (9 Nos. Model-8) (Group-27) | AE SWSD-I |  | ORD/000433/2021-2022 | 2215/SWD_I | 15/02/2022 | 01/04/2022 | SKILL AND FACILITY TRAINING INSTITUTE | 24.5 | 23.34 | 95.26 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-2) (Group-19) | AE BSD |  | ORD/000432/2021-2022 | 2269/SWD-I | 15/02/2022 | 01/04/2022 | I.B. ENTERPRISE | 7.13 | 4.49 | 63.03 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BARUIPUR block under South 24-Parganas W/S Division-I, PHE Dte. (19 Nos. Model-6) (Group-18) | AE BSD | JE-1 | ORD/000552/2021-2022 | 2193/SWD-I | 15/02/2022 | 16/04/2022 | KHAN ENTERPRISE | 50.24 | 33.58 | 66.84 | 90
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-2) (Group-25) | AE BSD,AE SWSD-I |  | ORD/000194/2021-2022 | 2257/SWD-I | 15/02/2022 | 01/04/2022 | GOUTAM MAZUMDER | 8.91 | 8.67 | 97.28 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (12 Nos. Model-6) (Group-33) | AE BSD,AE SWSD-I |  | ORD/000393/2021-2022 | 2211/SWD-I | 15/02/2022 | 16/04/2022 | PROJECT AND MAINTENANCE | 31.76 | 24.62 | 77.53 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (18 Nos. Model-6) (Group-29) | AE BSD,AE SWSD-I |  | ORD/000380/2021-2022 | 2197/SWD-I | 15/02/2022 | 16/04/2022 | S.P. CONSTRUCTION | 47.46 | 46.01 | 96.93 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-2) (Group-28) | AE BSD,AE SWSD-I |  | ORD/000352/2021-2022 | 2251/SWD-I | 15/02/2022 | 01/04/2022 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 10.69 | 10.39 | 97.2 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (16 Nos. Model-6) (Group-30) |  |  | ORD/000565/2021-2022 | 220.1/SWD-I | 15/02/2022 | 16/04/2022 | VISHAL CONSTRUCTION CO. | 41.76 | 17.66 | 42.29 | 100
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-I block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-8) (Group-32) | AE BSD,AE SWSD-I |  | ORD/000385/2021-2022 | 2239/SWD-I | 15/02/2022 | 01/04/2022 | SUKUMAR DEBNATH | 13.6 | 12.9 | 94.9 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 2106/SWD-I | 11/02/2022 | 11/02/2022 | Resource Division | 97.02 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 197 NOSIN BARUIPUR AND BUDGE BUDGE-I BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10114 | School | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 2108/SWD-I | 11/02/2022 | 11/02/2022 | Resource Division | 173.68 | 0 | 0 | 0
Total | [13 empty] | 675.76 | 321.08 | 47.51