## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-130) | AE BSD,AE SWSD-I |  | ORD/000182/2021-2022 | 2137/SWD-I | 15/02/2022 | 17/03/2022 | JYOTI ENTERPRISE | 2.64 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-154) | AE BSD,AE SWSD-I |  | ORD/000183/2021-2022 | 2161/SWD-I | 15/02/2022 | 17/03/2022 | JYOTI ENTERPRISE | 2.64 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-136) | AE BSD,AE SWSD-I |  | ORD/000189/2021-2022 | 2143/SWD-I | 15/02/2022 | 17/03/2022 | MODERN CONSTRUCTION | 2.64 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-123) | AE BSD,AE SWSD-I |  | ORD/000190/2021-2022 | 2130/SWD-I | 15/02/2022 | 17/03/2022 | MS POUSALI ENTERPRISE | 2.64 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-158) | AE BSD,AE SWSD-I |  | ORD/000187/2021-2022 | 2165/SWD-I | 15/02/2022 | 17/03/2022 | MS POUSALI ENTERPRISE | 2.64 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-135) | AE BSD,AE SWSD-I |  | ORD/000188/2021-2022 | 2142/SWD-I | 15/02/2022 | 17/03/2022 | MODERN CONSTRUCTION | 2.64 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-8) (Group-62) | AE BSD,AE SWSD-I |  | ORD/000181/2021-2022 | 2261/SWD-I | 15/02/2022 | 01/04/2022 | M/S. SREEJIT ENTERPRISE | 8.16 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-152) | AE BSD,AE SWSD-I |  | ORD/000184/2021-2022 | 2159/SWD-I | 15/02/2022 | 17/03/2022 | JYOTI ENTERPRISE | 2.64 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-124) | AE BSD,AE SWSD-I |  | ORD/000185/2021-2022 | 2131/SWD-I | 15/02/2022 | 17/03/2022 | MS POUSALI ENTERPRISE | 2.64 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-151) | AE BSD,AE SWSD-I |  | ORD/000202/2021-2022 | 2158/SWD-I | 15/02/2022 | 17/03/2022 | S.B. CONSTRUCTION | 2.64 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-145) | AE BSD,AE SWSD-I |  | ORD/000203/2021-2022 | 2152/SWD-I | 15/02/2022 | 17/03/2022 | S.B. CONSTRUCTION | 2.64 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-159) | AE BSD,AE SWSD-I |  | ORD/000201/2021-2022 | 2166/SWD-I | 15/02/2022 | 17/03/2022 | MS POUSALI ENTERPRISE | 2.64 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-134) | AE BSD,AE SWSD-I |  | ORD/000244/2021-2022 | 2141/SWD-I | 15/02/2022 | 17/03/2022 | J.P ENTERPRISE | 2.64 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | "Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-132)" | AE BSD,AE SWSD-I |  | ORD/000245/2021-2022 | 2139/SWD-I | 15/02/2022 | 17/03/2022 | J.P ENTERPRISE | 2.64 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-137) | AE BSD,AE SWSD-I |  | ORD/000242/2021-2022 | 2144/SWD-I | 15/02/2022 | 17/03/2022 | R.G ENTERPRISE | 2.64 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-131) | AE BSD,AE SWSD-I |  | ORD/000243/2021-2022 | 2138/SWD-I | 15/02/2022 | 17/03/2022 | J.P ENTERPRISE | 2.64 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-133) | AE BSD,AE SWSD-I |  | ORD/000246/2021-2022 | 2140/SWD-I | 15/02/2022 | 17/03/2022 | J.P ENTERPRISE | 2.64 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7) (Group-163) | AE BSD,AE SWSD-I |  | ORD/000247/2021-2022 | 2120/SWD-I | 15/02/2022 | 17/03/2022 | HASIBA ENTERPRISE | 2.67 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-141) | AE BSD,AE SWSD-I |  | ORD/000239/2021-2022 | 2148/SWD-I | 15/02/2022 | 17/03/2022 | GLOBUS CONSULTANCY | 2.64 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-150) | AE BSD,AE SWSD-I |  | ORD/000238/2021-2022 | 2157/SWD-I | 15/02/2022 | 17/03/2022 | B.R CONSTRUCTION | 2.64 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-144) | AE BSD,AE SWSD-I |  | ORD/000237/2021-2022 | 2151/SWD-I | 15/02/2022 | 17/03/2022 | B.R CONSTRUCTION | 2.64 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for AWCs as per different models of work under JOYNAGAR-I block under South 24-Parganas W/S Division-I, PHE Dte. (19 Nos. Model-6) (Group-60) | AE BSD,AE SWSD-I |  | ORD/000254/2021-2022 | 2194/SWD-I | 15/02/2022 | 16/04/2022 | BAIDYA ENTERPRISE | 50.3 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-155) | AE BSD,AE SWSD-I |  | ORD/000336/2021-2022 | 2162/SWD-I | 15/02/2022 | 15/02/2023 | B.R CONSTRUCTION | 2.64 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-146) | AE SWSD-I |  | ORD/000426/2021-2022 | 2153/SWD-I | 15/02/2022 | 17/03/2022 | SHAKAMBARI ENTERPRISES | 2.64 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-6) (Group-65) | AE BSD,AE SWSD-I |  | ORD/000248/2021-2022 | 2281/SWD-I | 15/02/2022 | 01/04/2022 | NANDY UDYOG | 5.3 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-140) | AE BSD,AE SWSD-I |  | ORD/000291/2021-2022 | 2147/SWD-I | 15/02/2022 | 17/03/2022 | ADITYA ENTERPRISE | 2.64 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-153) | AE BSD,AE SWSD-I |  | ORD/000292/2021-2022 | 2160/SWD-I | 15/02/2022 | 17/03/2022 | ADITYA ENTERPRISE | 2.64 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | "Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-162)" | AE BSD,AE SWSD-I |  | ORD/000250/2021-2022 | 2169/SWD-I | 15/02/2022 | 17/03/2022 | R.G ENTERPRISE | 2.64 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-2) (Group-34) | AE BSD,AE SWSD-I |  | ORD/000249/2021-2022 | 2270/SWD-I | 15/02/2022 | 01/04/2022 | SNEHA CONSTRUCTION | 7.13 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-161) | AE BSD,AE SWSD-I |  | ORD/000337/2021-2022 | 2168/SWD-I | 15/02/2022 | 17/03/2022 | M/S RUNA ENTERPRISE | 2.65 | 0 | 0 | 0
31 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-9) (Group-63) | AE BSD,AE SWSD-I |  | ORD/000345/2021-2022 | 2274/SWD-I | 15/02/2022 | 16/04/2022 | M/S. FAIZUL HAQUE BISWAS | 5.5 | 0 | 0 | 0
32 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-128) | AE BSD,AE SWSD-I |  | ORD/000350/2021-2022 | 2135/SWD-I | 15/02/2022 | 17/03/2022 | MOTIONMASS TECHNO OPC PVT LTD | 2.64 | 0 | 0 | 0
33 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-129) | AE BSD,AE SWSD-I |  | ORD/000349/2021-2022 | 2136/SWD-I | 15/02/2022 | 17/03/2022 | MOTIONMASS TECHNO OPC PVT LTD | 2.64 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-160) | AE BSD,AE SWSD-I |  | ORD/000351/2021-2022 | 2167/SWD-I | 15/02/2022 | 17/03/2022 | GLOBUS CONSULTANCY | 2.64 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-147) | AE BSD,AE SWSD-I |  | ORD/000353/2021-2022 | 2154/SWD-I | 15/02/2022 | 17/03/2022 | TKB ENTERPRISE | 2.65 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-148) | AE BSD,AE SWSD-I |  | ORD/000354/2021-2022 | 2155/SWD | 15/02/2022 | 17/03/2022 | M/S. SYSCON | 2.65 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7) (Group-166) | AE BSD,AE SWSD-I |  | ORD/000355/2021-2022 | 2123/SWD-I | 15/02/2022 | 17/03/2022 | GEO SOLUTION | 2.67 | 0 | 0 | 0
38 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for AWCs as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (11 Nos. Model-6) (Group-64) | AE BSD,AE SWSD-I |  | ORD/000368/2021-2022 | 2213/SWD-I | 15/02/2022 | 16/04/2022 | S.C. ENTERPRISE | 29.13 | 0 | 0 | 100
39 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-156) | AE BSD,AE SWSD-I |  | ORD/000370/2021-2022 | 2163/SWD-I | 15/02/2022 | 17/03/2022 | S.P. ENTERPRISE | 2.64 | 0 | 0 | 0
40 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-127) | AE BSD,AE SWSD-I |  | ORD/000365/2021-2022 | 2134/SWD-I | 15/02/2022 | 17/03/2022 | PS ENTERPRISE | 2.64 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-118) | AE BSD,AE SWSD-I |  | ORD/000373/2021-2022 | 2125/SWD-I | 15/02/2022 | 17/03/2022 | S.P. ENTERPRISE | 2.64 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-157) | AE BSD,AE SWSD-I |  | ORD/000371/2021-2022 | 2164/SWDI | 15/02/2022 | 17/03/2022 | S.P. ENTERPRISE | 2.64 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-119) | AE BSD,AE SWSD-I |  | ORD/000372/2021-2022 | 2126/SWD-I | 15/02/2022 | 17/03/2022 | S.P. ENTERPRISE | 2.64 | 0 | 0 | 0
44 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-126) | AE BSD,AE SWSD-I |  | ORD/000386/2021-2022 | 2133/SWD-I | 15/02/2022 | 17/03/2022 | A.M. ENTERPRISE (BASIRHAT) | 2.64 | 0 | 0 | 0
45 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-155) | AE BSD,AE SWSD-I |  | ORD/000376/2021-2022 | 2162/SWD-I NEW | 15/02/2022 | 17/03/2022 | S.R. CONSTRUCTION | 2.64 | 0 | 0 | 0
46 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7) (Group-164) | AE SWSD-I |  | ORD/000457/2021-2022 | 2121/SWD-I | 15/02/2022 | 17/03/2022 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 2.66 | 0 | 0 | 100
47 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-149) | AE SWSD-I |  | ORD/000456/2021-2022 | 2156/SWD-I | 15/02/2022 | 17/03/2022 | M/S. SYSCON | 2.65 | 0 | 0 | 100
48 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7) (Group-165) | AE SWSD-I |  | ORD/000458/2021-2022 | 2122/SWD-I | 15/02/2022 | 17/03/2022 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 2.66 | 0 | 0 | 100
49 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6) (Group-120) |  |  | ORD/000568/2021-2022 | 2127/SWD-I | 15/02/2022 | 17/03/2022 | M/S. SYSCON | 2.65 | 0 | 0 | 100
50 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 2100/SWD-I | 11/02/2022 | 11/02/2022 | Resource Division | 204.28 | 0 | 0 | 0
51 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 2101/SWD-I | 11/02/2022 | 11/02/2022 | Resource Division | 168.72 | 0 | 0 | 0
52 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under JOYNAGAR-I block under South 24-Parganas W/S Division-I, PHE Dte. (22 Nos. Model-6) (Group-61) [2nd Call]. | AE BSD,AE SWSD-I | JE-1 | ORD/000010/2022-2023 | 856/SWD-I | 12/07/2022 | 10/09/2022 | MS KRISHNA MONDAL | 58.01 | 0 | 0 | 90
53 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under JOYNAGAR-I block under South 24-Parganas W/S Division-I, PHE Dte. (25 Nos. Model-6) (Group-57) | AE BSD,AE SWSD-I | JE-2 | ORD/000260/2021-2022 | 2187/SWD-I | 15/02/2022 | 16/04/2022 | DIPALI CONSTRUCTION | 66.05 | 0 | 0 | 85
54 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1No. Model-6) (Group-138) | AE SWSD-I | JE-2 | ORD/000590/2021-2022 | 2145/SWD-I | 15/02/2022 | 17/03/2022 | SUMAN INDUSTRIES PVT LTD | 2.64 | 0 | 0 | 100
55 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1No. Model-6) (Group-139) | AE SWSD-I | JE-2 | ORD/000591/2021-2022 | 2146/SWD-I | 15/02/2022 | 17/03/2022 | SUMAN INDUSTRIES PVT LTD | 2.64 | 0 | 0 | 100
56 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 208 NOS IN JOYNAGAR-I AND THAKURPUKUR MAHESHTALA BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10116 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under THAKURPUKUR-MAHESHTALA block under South 24-Parganas W/S Division-I, PHE Dte. (1 Nos. Model-6) (Group-117) | AE SWSD-I | JE-1 | ORD/000587/2021-2022 | 2124/SWD-I | 15/02/2022 | 17/03/2022 | N. ENTERPRISE | 2.64 | 0 | 0 | 100
Total | [13 empty] | 724.2 | 0 | 0