## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (NARAYANPUR GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-2 and 1 No. Model-6) (Group-90) | AE HQ-I |  | ORD/000172/2021-2022 | 2272/SWD-I | 15/02/2022 | 01/04/2022 | NARAYAN ENTERPRISE | 6.21 | 5.26 | 84.72 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (NARAYANPUR GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (33 Nos. Model-6) (Group-93) | AE HQ-I |  | ORD/000332/2021-2022 | 2172/SWD-I | 15/02/2022 | 16/04/2022 | J.D. CONSTRUCTION | 87.31 | 86.4 | 98.95 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (NARAYANPUR GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-7) (Group-94) |  |  | ORD/000579/2021-2022 | 2277/SWD-I | 15/02/2022 | 01/04/2022 | R.G ENTERPRISE ( BHOWANIPORE) | 5.35 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (NARAYANPUR GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-3 and 1 No. Model-7) (Group-92) | AE HQ-I |  | ORD/000387/2021-2022 | 2118/SWD-I | 15/02/2022 | 17/03/2022 | S.R. CONSTRUCTION | 4.48 | 4.35 | 97.05 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (PARANGANJ GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (26 Nos. Model-6) (Group-87) | AE HQ-I |  | ORD/000395/2021-2022 | 2185/SWD-I | 15/02/2022 | 16/04/2022 | WALL FORT INDIA | 67.86 | 67.12 | 98.9 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (JAGULGACHI GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (27 Nos. Model-6) (Group-84) | AE HQ-I |  | ORD/000428/2021-2022 | 2184/SWD-I | 15/02/2022 | 16/04/2022 | MS S S ENTERPRISE DOMKOL | 71.49 | 69.9 | 97.78 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (NARAYANPUR GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-6) (Group-91) | AE HQ-I |  | ORD/000464/2021-2022 | 2266/SWD-I | 15/02/2022 | 01/04/2022 | MANIRUL ISLAM | 7.94 | 7.86 | 98.93 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (PARANGANJ GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-7) (Group-89) |  |  | ORD/000567/2021-2022 | 2264/SWD-I | 15/02/2022 | 01/04/2022 | SHYAMAL MONDAL | 7.99 | 7.85 | 98.28 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (PARANGANJ GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (13 Nos. Model-6) (Group-88) |  |  | ORD/000564/2021-2022 | 22009/SWD-I | 15/02/2022 | 16/04/2022 | M/S L.P CONSTRUCTION | 34.28 | 33.8 | 98.6 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (CH-II GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 3 Nos. Model-6) (Group-102) |  |  | ORD/000563/2021-2022 | 2242/SWD-I | 15/02/2022 | 01/04/2022 | M/S L.P CONSTRUCTION | 13.29 | 7.88 | 59.26 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (PARANGANJ GP of BHANGAR AC) under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-6) (Group-86) [2nd Call] |  |  | ORD/000582/2021-2022 | 2618/SWD-I | 16/03/2022 | 30/04/2022 | PROJECT AND MAINTENANCE | 15.88 | 15.63 | 98.44 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC ) 132 NOS IN JAGULGACHI, PRANGANJ AND NARAYANPUR GPS OF BHANGAR-I BLOCK (BHANGAR A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10119 | School | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 2107/SWD-I | 11/02/2022 | 11/02/2022 | Resource Division | 181.07 | 0 | 0 | 0
Total | [13 empty] | 503.16 | 306.04 | 60.82