## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Chemical, Glassware & Instruments requirement and allied Civil, Electro Mechanical works for NABL Accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Amtala Sub Division under South 24 Parganas W/S Division-I. | SM/10196 | Support-WQMSP | Chemical, glassware & instruments requirement part for NABL accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under South 24-Pgns. W/S Division-I, PHE DTE. in the district of South 24 Pgs. |  |  | VCH/000100/2022-2023 | BP-2022-23-10 | 27/04/2022 | 27/04/2022 | DULAL MAJUMDER | 11.29 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Chemical, Glassware & Instruments requirement and allied Civil, Electro Mechanical works for NABL Accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Amtala Sub Division under South 24 Parganas W/S Division-I. | SM/10196 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory at Amtala including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-II |  | ORD/000236/2021-2022 | 1332/SWD-I | 24/11/2021 | 22/02/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.81 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Chemical, Glassware & Instruments requirement and allied Civil, Electro Mechanical works for NABL Accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Amtala Sub Division under South 24 Parganas W/S Division-I. | SM/10196 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Amtala Sub District Water Testing Laboratory, under South 24-Pgs. W/S Divn.-I, P.H.E. Dte. (SM/10196) | AE SWSD-II | JE2 | ORD/000544/2023-2024 | 2492/SWD-I | 06/10/2023 | 06/10/2024 | M/S LAXMI ENTERPRISE | 0.82 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Chemical, Glassware & Instruments requirement and allied Civil, Electro Mechanical works for NABL Accreditation at Amtala Sub District Water Testing Laboratory as per ISO/IEC:17025:217 under Amtala Sub Division under South 24 Parganas W/S Division-I. | SM/10196 | Support-WQMSP | Furnitures required for NABL Accreditation at Amtala Sub-District Water Testing Laboratory as per ISO/IEC: 17025:217 under Amtala Sub-Division under South 24 pgs W/S Division-I, P.H.E Dte. (SM/10196) | AE SWSD-II | JE2 | ORD/000745/2023-2024 | 550/SWD-I | 31/01/2024 | 07/02/2024 | SRIJON ENTERPRISE | 3.96 | 0 | 0 | 100
Total | [13 empty] | 18.87 | 0 | 0