## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Fabrication, Supplying, Fitting and Installation of Laboratory New Furniture for upgradation in facilitate suitable environmental condition as per norms of ISO/IEC 17025 : 2017 (Clause 6.3) of State Referral Laboratory of West Bengal at Dakshin Roypur Water Treatment Plant under South 24 Pgs W/S Division-I, PHE Dte | AE SWSD-I |  | ORD/000057/2021-2022 | 897/SWD-I | 22/09/2021 | 06/11/2021 | BILASH ENTERPRISE | 23.45 | 23.45 | 100 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Fibre optic network for better Internet Service to maintain data uploading in IMIS and keeping data safe and new configuration Computer and other pheripherals as per ISO/IEC 17025 : 2017 (Clause No.: 8.4.2) at State Referral Laboratory of West Bengal at Dakshin Roypur Water Treatement Plant under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000235/2021-2022 | 2668/SWD-I | 23/03/2022 | 23/03/2023 | WEBEL TECHNOLOGY LTD | 15.38 | 15.38 | 100 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Modification of Bacteriological Laboratory in accordance to IS 15185 : 2016 for accreditation of ISO/IEC - 17025 : 2017 with allied accessories for ICP-OES & AAS at State Referral Laboratory of West Bengal at Dakshin Roypur Water Treatement Plant under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I | JE-2 | ORD/000063/2022-2023 | 1101/SWD-I | 22/08/2022 | 01/02/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 27.39 | 25.2 | 91.98 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Development of infrastructure at Dakshin Raipur Water Treatment Plant Laboratory of chemical unit and other allied units in tune with the protocols of ISO/IEC 17025 : 2017 under South 24-Pgns. W/S Division-I, PHE Dte | AE SWSD-I |  | ORD/000256/2021-2022 | 1822/SWD-I | 19/01/2022 | 20/03/2022 | CALCON CONSTRUCTIONS | 11.51 | 10.91 | 94.77 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Development of infrastructure at Dakshin Raipur Water Treatment Plant Laboratory for Bacteriological unit with allied works in tune with the protocols of ISO/IEC 17025 : 2017 under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000295/2021-2022 | 1821/SWD-I | 19/01/2022 | 20/03/2022 | MS RAMJIBAN SHARMA | 10.92 | 10.84 | 99.29 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Upgradation and accreditation of Bacteriological testing scope of State Level Laboratory at Dakshin Roypur WTP campus with allied works (As per ISO/IEC 17025:2017) under S-24Pgns W/S Divn-I (Phase-I) | SM/10197 | Support-WQMSP | Balance work for Bacteriological Laboratory in accordance to IS 15185 : 2016 for accreditation of ISO/IEC - 17025 : 2017 with allied accessories for ICP-OES & AAS at State Referral Laboratory of West Bengal at Dakshin Roypur Water Treatement Plant under South 24 Pgs W/S Division-I, PHE Dte. (TSM/005807) | AE SWSD-I | JE-2 | ORD/000425/2023-2024 | 1592/SWD-I | 31/07/2023 | 30/08/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 17.5 | 17.5 | 100 | 20
Total | [13 empty] | 106.16 | 103.28 | 97.29