## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Electricity Bill |  |  | VCH/003873/2022-2023 | 65/PFMS | 11/11/2022 | 11/11/2022 | CESC LTD | 2.78 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Supply, installation & Commissioning of 30 KVA voltage stabilizer at Asuti-I&II Gram Panchayet area Block-Thakurpukur Maheshtala under South 24-Pgs Mechanical Division PHE Dte. |  |  | ORD/003625/2021-2022 | 868/SMD. | 28/07/2021 | 27/08/2021 | S.P. CONSTRUCTION | 3.93 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Land Development of Ganney Gangadharpur OHR (1250 cum capacity) Head work Site under Asuti I / Asuti II W/S Scheme under South 24 Pgns W/S Div I , PHED. | AE SWSD-I |  | ORD/000041/2022-2023 | 441/SWD-I | 24/05/2022 | 08/06/2022 | MS POUSALI ENTERPRISE | 4.61 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Asuti-2 of Asuti 1& 2 Gram Panchayet area under Thakupukur Maheshtala Block under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/002721/2021-2022 | 915/SMD. | 09/08/2021 | 07/11/2021 | A.K.SIKDAR | 6.35 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no.1 of Chata Gram Panchayet area under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/003330/2021-2022 | 914/SMD. | 09/08/2021 | 07/11/2021 | J.K. ENGINEERING CO. | 5.81 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1660 | 21/10/2022 | 21/10/2022 | Resource Division | 66.08 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 560 | 27/07/2022 | 27/07/2022 | Resource Division | 417.66 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 2008/SWD-I | 28/08/2023 | 28/08/2023 | Resource Division | 15.6 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01060/2023-2024 | BP-2023-24-127 | 17/07/2023 | 17/07/2023 | CESC LTD | 1.98 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2023 to 30/11/2023] | AE SWSD-I |  | ORD/000290/2023-2024 | 702/SWD-I | 26/05/2023 | 25/11/2023 | AVIK HALDER | 0.89 | 0 | 0 | 30
11 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | S24 Pgns Mechanical | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05979/2023-2024 | BP-2023-24-634 | 29/03/2024 | 29/03/2024 | CESC LTD | 2.9 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Laying of Distribution System, Road Restoration including providing FHTC for Asuti-I & II GP and adjoining areas under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, P.H.E. Dte., District-South 24 Parganas. | AE SWSD-I | JE-1 | ORD/000065/2022-2023 | 1110/SWD-I | 23/08/2022 | 29/07/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1559.44 | 0 | 0 | 80
13 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I | JE-1,JE-2 | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 30/04/2025 | WATREAT ENGINEERS | 184.41 | 0 | 0 | 50
14 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Laying of 63mm & 75mm dia pipeline for PWSS of Asuti-I & Asuti-II GP in Thakurpukur-Maheshtala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11160) | AE SWSD-I | JE-1 | ORD/000115/2023-2024 | 527/SWD-I | 11/05/2023 | 02/08/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 122.8 | 0 | 0 | 80
15 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | SM/11160 | New | Modification of foundation of awarded 1500 Cum. OHR at Chatta as per sustainability and best engineering practice including site development under ¿Water Supply Arrangement for Asuti I/II and Chatta GP¿ under South 24 Pgns. W/S Divn.-I, PHED. [TSM/005082] [2nd Call] | AE SWSD-I | JE-2 | ORD/000074/2022-2023 | 1160/SWD-I | 29/08/2022 | 20/02/2025 | M/S. S.S. ENTERPRISE | 34.1 | 0 | 0 | 90
Total | [13 empty] | 2429.34 | 0 | 0