## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11235 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-VII at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 9193] | AE HQ-I | JE-3 | ORD/000053/2023-2024 | 272/SWD-I | 24/04/2023 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 591.54 | 79.39 | 13.42 | 35
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11235 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 56.63 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11235 | Retrofitting | Continuation order for the work of Supply of various D.I. fittings of different diameters for laying of pipeline in connection Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | AE HQ-I | JE-3 | ORD/000778/2024-2025 | 4174/SWD-I | 25/09/2024 | 10/10/2024 | B.S. RUBBER INDUSTRIES | 5.81 | 5.59 | 96.25 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11235 | Retrofitting | Road Restoration and Bullah Piling work for laying of distribution pipes between node point from 1 to 2, 2 to 47, 47 to 48, 48 to 49, 49 to 50, 50 to 51, 51 to 52 for Laying Distribution System to extend the benefit of 100% FHTC at Mandirbazar Block in Zone VII within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. [SM/11235] | AE HQ-I | JE-3 | ORD/000520/2024-2025 | 4013/SWD-I | 13/09/2024 | 24/08/2025 | BISWAS CONSTRUCTION | 25.33 | 7.1 | 28.03 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11235 | Retrofitting | Supply of various D.I. fittings of different diameters for laying of pipeline in connection Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | AE HQ-I | JE-3 | ORD/000348/2024-2025 | 3377/SWD-I | 27/07/2024 | 26/08/2024 | B.S. RUBBER INDUSTRIES | 11.6 | 11.6 | 100 | 100
Total | [13 empty] | 690.91 | 103.68 | 15.01