## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11237 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 35.04 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11237 | Retrofitting | Road Restoration and Bullah Piling work for laying of distribution pipes between node point from 1 to 2, 2 to 59, 59 to 60, 60 to 61, 61 to 62, 62 to 63, 63 to 64, 64 to 65 for Laying Distribution System to extend the benefit of 100% FHTC at Mandirbazar Block in Zone X within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. [SM/11237] | AE HQ-I | JE-3 | ORD/000521/2024-2025 | 4014/SWD-I | 13/09/2024 | 27/01/2025 | BISWAS CONSTRUCTION | 42.19 | 0 | 0 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11237 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-X at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5689] | AE HQ-I | JE-3 | ORD/000616/2022-2023 | 3216/SWD-I | 28/02/2023 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 379.55 | 12.07 | 3.18 | 30
Total | [13 empty] | 456.79 | 12.07 | 2.64