## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-IX at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11238 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 21.15 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-IX at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11238 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-IX at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3434] | AE HQ-I,AE HQ-II | JE-3 | ORD/000617/2022-2023 | 3217/SWD-I | 28/02/2023 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 250.59 | 0 | 0 | 15
Total | [13 empty] | 271.75 | 0 | 0