## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11240 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Zone-VI at Mandirbazar block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. (TSM/010830) [10th SLSSC (2021-22)] | AE HQ-I,AE HQ-II | JE-3 | ORD/000770/2022-2023 | 3644/SWD-I | 28/03/2023 | 30/06/2025 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 192.73 | 30.44 | 15.79 | 55
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-VI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11240 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 19.44 | 0 | 0 | 0
Total | [13 empty] | 212.17 | 30.44 | 14.35