## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11243 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 59.25 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11243 | Retrofitting | Laying of 600 mm dia DI Secondary Grid pipeline including allied works infront of Mandirbazar GLR & Bijoyganj Bazar (gap negotiation) within Mandirbazar Block in connection with Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply scheme for Falta-Mathurapur, Dist. South 24-pgs. under South 24-Pgns W/S Division-I, PHE Dte. (SM/11243) | AE HQ-II | JE-3 | ORD/000798/2023-2024 | 1146/SWD-I | 07/03/2024 | 06/04/2024 | S. ROY AND ASSOCIATES | 39.85 | 29.31 | 73.55 | 90
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11243 | Retrofitting | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I | JE-3 | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 01/04/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 51.23 | 3.07 | 20
Total | [13 empty] | 1766.94 | 80.54 | 4.56