## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-III at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte | SM/11244 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 3015/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 47.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in Zone-III at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte | SM/11244 | Retrofitting | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I,AE HQ-II | JE-3 | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 02/06/2025 | SUPRITI ENTERPRISE | 1557.57 | 0 | 0 | 50
Total | [13 empty] | 1605.09 | 0 | 0