## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE- VIII AT NIMPITH MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11246 | Augmentation | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-VIII at Nimpith Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000201/2022-2023 | 1557/SWD-I | 13/10/2022 | 09/08/2023 | RAJ BROTHERS | 268.09 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE- VIII AT NIMPITH MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11246 | Augmentation | Providing 100% FHTC in Zone-VIII at Nimpith mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 7302] | AE BSD | JE RWS,JE-2 | ORD/000345/2022-2023 | 2150/SWD-I | 08/12/2022 | 26/02/2025 | M/S. S.S. ENTERPRISE | 556.22 | 242.52 | 43.6 | 75
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE- VIII AT NIMPITH MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11246 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 3001/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 44.98 | 0 | 0 | 0
Total | [13 empty] | 869.29 | 242.52 | 27.9