## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT MONIRTAT MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11247 | Augmentation | Providing 100% FHTC in Zone-V A at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4150] | AE BSD |  | ORD/000270/2023-2024 | 1550/SWD-I | 25/07/2023 | 22/11/2023 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 316.11 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT MONIRTAT MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11247 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 2998/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 49.95 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT MONIRTAT MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11247 | Augmentation | Providing 100% FHTC in Zone-V B at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3958] | AE BSD | JE-1 | ORD/000813/2022-2023 | 3692/SWD-I | 30/03/2023 | 28/07/2023 | CALCON CONSTRUCTIONS | 299.61 | 39.88 | 13.31 | 30
Total | [13 empty] | 665.66 | 39.88 | 5.99