## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11250 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 2990/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 57.93 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11250 | Augmentation | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 09/07/2022 | MANASH GHOSH | 626.38 | 213.82 | 34.14 | 91
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11250 | Augmentation | Providing 100% FHTC in Zone-III B at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4773] | AE BSD | JE-1 | ORD/000588/2022-2023 | 3123/SWD-I | 24/02/2023 | 24/06/2023 | MANASH GHOSH | 363.26 | 130.59 | 35.95 | 50
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MONDOLER LAT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11250 | Augmentation | Providing 100% FHTC in Zone-III A at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4631] | AE BSD | JE-2 | ORD/000031/2023-2024 | 115/SWD-I | 11/04/2023 | 09/08/2023 | SUPRITI ENTERPRISE | 352.02 | 141.48 | 40.19 | 30
Total | [13 empty] | 1399.59 | 485.89 | 34.72