## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT JALABERIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11251 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 2989/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 57.92 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT JALABERIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11251 | Augmentation | Providing 100% FHTC in Zone-II B at Jalaberia mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4835] | AE BSD | JE-1 | ORD/000218/2022-2023 | 1627/SWD-I | 20/10/2022 | 24/11/2025 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 367.31 | 0 | 0 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT JALABERIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11251 | Augmentation | Providing 100% FHTC in Zone-II A at Jalaberia mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur district.- South 24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4568] | AE BSD | JE-2 | ORD/000524/2023-2024 | 2306/SWD-I | 20/09/2023 | 10/08/2025 | SPA ENTERPRISE | 365.25 | 0 | 0 | 40
Total | [13 empty] | 790.48 | 0 | 0