## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11253 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 2992/SWD-I | 20/02/2023 |  | Resource Division | 41.82 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11253 | New | Providing 100% FHTC in Zone-VI B at Madhya Gurguria mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3487] | AE BSD | JE-1 | ORD/000460/2023-2024 | 2137/SWD-I | 31/08/2023 | 29/11/2023 | M/S SARADA CONSTRUCTION | 280.24 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11253 | New | Providing 100% FHTC in Zone-VI A at Madhya Gurguria mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3302] | AE BSD | JE-2 | ORD/000183/2022-2023 | 1486/SWD-I | 28/09/2022 | 26/01/2023 | MS GOUTAM CHAKRABORTY | 252.19 | 29.69 | 11.77 | 40
Total | [13 empty] | 574.25 | 29.69 | 5.17