## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II B (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. |  |  | ORD/001036/2022-2023 | 1065/SWD-I | 12/08/2022 | 27/08/2022 | S.K. ENTERPRISE | 0.72 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II A (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. |  |  | ORD/001037/2022-2023 | 1066/SWD-I | 12/08/2022 | 27/08/2022 | S.K. ENTERPRISE | 3.18 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | Providing 100% FHTC in Zone-II B at Mayahauri mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3400] | AE BSD | JE-1 | ORD/000534/2022-2023 | 2966/SWD-I | 17/02/2023 | 17/06/2023 | PRITAM SENGUPTA (EMAIL ID-SENGUPTA408@YAHOO.COM) | 207.24 | 25.63 | 12.37 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | SupplyofdifferentCIDFspecialsfor layingof DIpipe(250mm dia & 400mm dia)at zone-II B (Mayahauri)of Joynagar-II Blockof BaruipurSub-Division, for "MegaSurface Based water supply schemeforFalta-Mathurapur, DistrictSouth24-Pgns, W/S Division-I, PHE. Dte. |  |  | ORD/000998/2022-2023 | 1073/SWD-I | 16/08/2022 | 31/08/2022 | S.K. ENTERPRISE | 0.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | Providing 100% FHTC in Zone-II A at Mayahauri mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [ No. of FHTC = 5789 ] | AE BSD | JE-2 | ORD/000370/2022-2023 | 2314/SWD-I | 19/12/2022 | 07/04/2025 | SAMIRON GHOSH | 440.83 | 102.66 | 23.29 | 50
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-II A & ZONE-II B AT MAYAHAURI MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11255 | Augmentation | Supply of different CIDF specials for layingof DIpipeat zone-II A (Mayahauri)of Joynagar-II Block of Baruipur Sub-Division, for "Mega Surface Based water supply scheme for Falta-Mathurapur, District South 24-Pgns, W/S Division-I, PHE. Dte. | AE BSD | JE-2 | ORD/000999/2022-2023 | 1072/SWD-I | 16/08/2022 | 31/08/2022 | S.K. ENTERPRISE | 3.18 | 0 | 0 | 80
Total | [13 empty] | 655.87 | 128.29 | 19.56