## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-III A & ZONE-III B AT BELADURGANAGAR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11256 | Augmentation | Providing 100% FHTC in Zone-III A at Beladurganagar mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3828] | AE BSD | JE-2 | ORD/000271/2023-2024 | 1551/SWD-I | 25/07/2023 | 22/11/2023 | M/S LOKENATH CONSTRUCTION | 289.12 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-III A & ZONE-III B AT BELADURGANAGAR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11256 | Augmentation | Providing 100% FHTC in Zone-III B at Beladurganagar mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC= 3903] | AE BSD | JE-1 | ORD/000269/2023-2024 | 1549/SWD-I | 25/07/2023 | 22/11/2023 | AJIT PRAMANICK | 294.9 | 69.1 | 23.43 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-III A & ZONE-III B AT BELADURGANAGAR MOUZA OF JOYNAGAR-II BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | SM/11256 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 2996/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 47.62 | 0 | 0 | 0
Total | [13 empty] | 631.64 | 69.1 | 10.94