## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT KATAMARI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11257 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 3002/SWD-I | 20/02/2023 |  | Resource Division | 520.49 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT KATAMARI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11257 | New | Providing 100% FHTC in Zone-V B at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4346] | AE BSD,AE SWSD-I | JE-1 | ORD/000155/2023-2024 | 806/SWD-I | 02/06/2023 | 30/09/2023 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 330.69 | 21.04 | 6.36 | 30
3 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE-V A & ZONE-V B AT KATAMARI MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11257 | New | Providing 100% FHTC in Zone-V A at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5791] | AE BSD,AE SWSD-I | JE-1 | ORD/000156/2023-2024 | 807/SWD-I | 02/06/2023 | 30/09/2023 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 440.56 | 70.55 | 16.01 | 35
Total | [13 empty] | 1291.74 | 91.6 | 7.09