## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11262 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 29.44 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11262 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 234.99 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11262 | Retrofitting | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | AE SWSD-II,Assistant Engineer | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 02/04/2025 | TARUN ENTERPRISE | 922.07 | 48.35 | 5.24 | 70
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11262 | Retrofitting | Three months trial run for Secondary Grid for Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [SM/11262] [w.e.f. 01/02/2025 to 01/05/2025] | AE SWSD-II | JE2 | ORD/001128/2024-2025 | 191/SWD-I | 17/01/2025 | 02/05/2025 | AVIK ENTERPRISE | 30.87 | 0 | 0 | 90
Total | [13 empty] | 1217.37 | 48.35 | 3.97